## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002045/2022-2023 | 13045/AD | 24/03/2023 | 08/05/2023 | BINAPANI ENTERPRISE | 8.92 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gopalkata water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000549/2022-2023 | 475/SMD | 20/02/2023 | 21/05/2023 | P.K. ENGINEERING | 19.27 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Inter connection and rising main with supply of specials of Augmentation of Gopalkata W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000124/2023-2024 | 570/AD | 12/05/2023 | 27/05/2023 | M/S MANGALCHANDI CONSTRUCTION | 7.59 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Gopalkata New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001883/2022-2023 | 7596/AD | 28/11/2022 | 12/01/2023 | M/S R.DUTTA & CO. | 3.28 | 0 | 0 | 95
5 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 382/AD | 02/05/2023 | 02/05/2023 | Resource Division | 11.74 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Construction of 100 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Gopalkata piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 888] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000295/2023-2024 | 3732/AD | 03/11/2023 | 29/08/2024 | CHAKRABORTTI ENTERPRISE | 258.61 | 0 | 0 | 55
7 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Construction of boundary wall at Head Work Sitefor Ground water Based at Gopalkata Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000737/2024-2025 | 4395/AD | 05/11/2024 | 20/12/2024 | SUBHO CONSTRUCTION | 32.48 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Construction of boundary wall at Pump House No- 2 for Ground water Based at Gopalkata Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000738/2024-2025 | 4407/AD | 05/11/2024 | 05/12/2024 | M/S. BISWAS CONSTRUCTION(I) | 19.52 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000215/2023-2024 | 955/AD | 06/06/2023 | 02/08/2023 | SALMAN CONSTRUCTION | 43.94 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED GOPALKATA PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13834 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002046/2022-2023 | 13046/AD | 24/03/2023 | 01/03/2025 | BINAPANI ENTERPRISE | 8.61 | 0 | 0 | 100
Total | [13 empty] | 413.96 | 0 | 0