## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Jelepara New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001884/2022-2023 | 7597/AD | 28/11/2022 | 12/01/2023 | M/S R.DUTTA & CO. | 3.32 | 3.32 | 100 | 95
2 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Jelepara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000550/2022-2023 | 476/SMD | 20/02/2023 | 04/07/2025 | P.K. ENGINEERING | 19.27 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Construction of OHR (100 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the JELEPARA, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000060/2023-2024 | 310/AD | 26/04/2023 | 20/02/2024 | ADITYA HAZRA | 244.02 | 74.57 | 30.56 | 60
4 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Inter connection and rising main with supply of specials of Augmentation of Jelepara W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000147/2023-2024 | 693/AD | 18/05/2023 | 01/04/2025 | JOY ENGINEERING & CONSTRUCTION | 11.83 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Jelepara W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000216/2023-2024 | 956/AD | 06/06/2023 | 01/03/2024 | INDIA CONSTRUCTION | 43.94 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Jelepara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001579/2022-2023 | 10683/AD | 01/02/2023 | 18/03/2023 | SARDAR ENTERPRISE | 8.87 | 8.7 | 98.06 | 100
7 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Jelepara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001820/2022-2023 | 12335/AD | 06/03/2023 | 20/04/2023 | SARDAR ENTERPRISE | 8.59 | 8.38 | 97.55 | 100
8 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 1058/AD | 15/06/2023 | 15/06/2023 | Resource Division | 4.64 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 248/AD | 24/04/2023 | 24/04/2023 | Resource Division | 40.56 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04081/2023-2024 | BP-2023-24-419 | 16/12/2023 | 16/12/2023 | WBSEDCL | 7.55 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Construction of boundary wall at Pump House No. - 2 for Ground Water Based at Jelepara Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000736/2024-2025 | 4394/AD | 05/11/2024 | 01/03/2025 | SARDAR ENTERPRISE | 14.29 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Supply & delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Jelepara PH-1 water supply scheme under Gosaba Block under SMD, PHE Dte. (SM/13836) | Assistant Engineer | Junior Engineer | ORD/002510/2024-2025 | 1708/SMSD | 27/12/2024 | 11/01/2025 | P.K. ENGINEERING | 0.99 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Supply & delivery of Cast Iron wafer type butterfly valve with 3 phase actuator at Jelepara PH-2 water supply scheme under Gosaba Block under SMD, PHE Dte. (SM/13836) | Assistant Engineer | Junior Engineer | ORD/002511/2024-2025 | 1707/SMSD | 27/12/2024 | 11/01/2025 | P.K. ENGINEERING | 0.99 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Improvement of outdoor illumination arrangement with allied works at Pump House-1 of Jelepara water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/13836) | Assistant Engineer | Junior Engineer | ORD/002515/2024-2025 | 1771/SMSD | 31/12/2024 | 15/01/2025 | P.K. ENGINEERING | 0.97 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Supply & delivery of valve and UPVC column pipe etc at Jelepara PH-1 water supply scheme under SMD, P.H.E. Dte. [SM/13836] | Assistant Engineer | Junior Engineer | ORD/002512/2024-2025 | 1675/A/SMSD | 20/12/2024 | 04/01/2025 | P.K. ENGINEERING | 0.7 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Supply & delivery of valve and UPVC column pipe etc at Jelepara PH-2 water supply scheme under SMD, P.H.E. Dte. [SM/13836] | Assistant Engineer | Junior Engineer | ORD/002513/2024-2025 | 1673-A/SMSD | 20/12/2024 | 04/01/2025 | P.K. ENGINEERING | 0.7 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Supply & fixing main switch & Bus Bar at Pump House-1 of Jelepara water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/13836) | Assistant Engineer | Junior Engineer | ORD/002514/2024-2025 | 1772/SMSD | 31/12/2024 | 15/01/2025 | P.K. ENGINEERING | 0.31 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Supply & fixing main switch & Bus Bar at Pump House-2 of Jelepara water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/13836) | Assistant Engineer | Junior Engineer | ORD/002516/2024-2025 | 283/SMSD | 25/02/2025 | 12/03/2025 | P.K. ENGINEERING | 0.31 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Improvement of outdoor illumination arrangement with allied works at Pump House-2 of Jelepara water supply sche under SMD,PHE Dte. (Block-Gosaba) (SM/13836) | Assistant Engineer | Junior Engineer | ORD/002517/2024-2025 | 282/SMSD | 25/02/2025 | 12/03/2025 | P.K. ENGINEERING | 0.97 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED JELEPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13836 | New | Quotation for new service( power) connection at Jelepara PH-2 Water supply scheme under Gosaba block. Reference ID:-106841449, Application No :-1008235023 |  |  | BILL/02416/2024-2025 | BP-2024-25-524 | 10/01/2025 | 10/01/2025 | WBSEDCL | 4.45 | 0 | 0 | 0
Total | [13 empty] | 417.24 | 94.97 | 22.76