## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamakhyapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000551/2022-2023 | 490/SMD | 20/02/2023 | 21/05/2023 | AVINABA ENGINEERING CONCERN | 20.09 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Kamakshyapur New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001885/2022-2023 | 7598/AD | 28/11/2022 | 12/01/2023 | M/S R.DUTTA & CO. | 5.39 | 5.39 | 100 | 95
3 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 381/AD | 02/05/2023 | 02/05/2023 | Resource Division | 30.19 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Construction of OHR (200 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KAMAKHYAPUR, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000062/2023-2024 | 312/AD | 26/04/2023 | 20/02/2024 | SAMSUL ENTERPRISE | 432.74 | 162.18 | 37.48 | 30
5 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Laying of additional pipe line and other allied works at Kamakhyapur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000542/2024-2025 | 3713/AD | 12/09/2024 | 11/11/2024 | SAMSUL ENTERPRISE | 60.04 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000217/2023-2024 | 957/AD | 30/05/2023 | 03/08/2023 | INDIA CONSTRUCTION | 43.94 | 39.16 | 89.11 | 100
7 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Quotation for new service( power) connection at Kamakhyapur TW-02 Water supply scheme under Gosaba block. Reference ID:-106763781, Application No :-1008116807 |  |  | BILL/01843/2024-2025 | BP-2024-25-471 | 18/11/2024 | 18/11/2024 | WBSEDCL | 7.57 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Inter connection and rising main with supply of specials of Augmentation of Kamakhyapur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001083/2023-2024 | 3542/AD | 17/10/2023 | 01/11/2025 | GHOSH CONSTRUCTION | 11 | 0 | 0 | 80
9 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Construction of boundary wall at Head Work Site for Ground Water Based at Kamakhyapur Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000120/2025-2026 | 2583/AD | 03/06/2025 | 18/07/2025 | JHARNA CONSTRUCTION | 37.41 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001762/2022-2023 | 11944/AD | 24/02/2023 | 01/02/2025 | BANGA NIRMAN | 8.61 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002111/2022-2023 | 12877/AD | 17/03/2023 | 01/01/2025 | JOY GURU BUILDERS | 8.92 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED KAMAKHYAPUR PIPEWATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK GOSABA, DISTRICT SOUTH 24 PARGANAS. | SM/13837 | New | Quotation for new service( power) connection at Kamakhyapur PH-1 Water supply scheme under Gosaba block. Reference ID:-106860940, Application No :-1008267185 |  |  | BILL/02509/2024-2025 | BP-2024-25-554 | 27/01/2025 | 27/01/2025 | WBSEDCL | 4.06 | 0 | 0 | 0
Total | [13 empty] | 669.97 | 206.72 | 30.86