## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kamarpara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000552/2022-2023 | 497/SMD | 20/02/2023 | 21/05/2023 | AVINABA ENGINEERING CONCERN | 20.09 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Inter connection and rising main with supply of specials of Augmentation of Kamarpara W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000732/2023-2024 | 2893/AD | 19/09/2023 | 04/10/2023 | M/S. MIHIR KUMAR NASKAR | 13.26 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Kamarpara New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001886/2022-2023 | 7599/AD | 28/11/2022 | 12/01/2023 | M/S R.DUTTA & CO. | 4.49 | 0 | 0 | 95
4 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 251/AD | 24/04/2023 | 24/04/2023 | Resource Division | 50.79 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 1047/AD | 15/06/2023 | 15/06/2023 | Resource Division | 8.89 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Construction of boundary wall at Pump House No-2 at Kamarpara Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000735/2024-2025 | 4393/AD | 05/11/2024 | 05/12/2024 | SUKUMAR HALDAR | 14.97 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000386/2023-2024 | 1575/AD | 17/07/2023 | 10/09/2023 | GIASHUDDIN CONSTRUCTION | 43.94 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Kamarpara piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1443] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000293/2023-2024 | 1503/AD | 15/07/2023 | 15/04/2026 | PROJECT INDIA | 354.06 | 0 | 0 | 85
9 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Construction of boundary wall at Head Work Sitef or Ground water Based at Kamarpara Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000388/2025-2026 | 3373/AD | 16/07/2025 | 30/08/2025 | SWASTIK CONSTRUCTION | 32.27 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000253/2023-2024 | 1396/AD | 12/07/2023 | 01/02/2025 | RAKTIM ENTERPRISE | 8.88 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED KAMARPARA PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/13838 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000254/2023-2024 | 1397/AD | 12/07/2023 | 01/01/2025 | RAKTIM ENTERPRISE | 8.57 | 0 | 0 | 100
Total | [13 empty] | 560.21 | 0 | 0