## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Birprosadpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000809/2022-2023 | 774/SMD | 17/03/2023 | 15/06/2023 | P.K. ENGINEERING | 19.27 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Biprodaspur W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000384/2023-2024 | 1518/AD | 15/07/2023 | 29/08/2023 | PURKAIT CONSTRUCTION | 43.92 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Biprodaspur New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001882/2022-2023 | 7524/AD | 28/11/2022 | 12/01/2023 | M/S R.DUTTA & CO. | 4.94 | 0 | 0 | 99
4 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 1048/AD | 15/06/2023 | 15/06/2023 | Resource Division | 9.03 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 250/AD | 24/04/2023 | 24/04/2023 | Resource Division | 45.11 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Construction of 150 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Pipes W/S Scheme for Biprodaspur Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1466] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000041/2023-2024 | 176/AD | 19/04/2023 | 13/02/2024 | I.S. ENTERPRISE | 423.65 | 0 | 0 | 25
7 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bipradaspur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000297/2024-2025 | 2667/AD | 21/06/2024 | 05/08/2024 | REZU CONSTRUCTION | 8.61 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Bipradaspur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000296/2024-2025 | 2666/AD | 21/06/2024 | 05/08/2024 | REZU CONSTRUCTION | 8.92 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Quotation for new service( power) connection at Biprodaspur PH-1 Water supply scheme under Gosaba block. Reference ID:-106763780, Application No :-1008116731 |  |  | BILL/01844/2024-2025 | BP-2024-25-470 | 18/11/2024 | 18/11/2024 | WBSEDCL | 7.92 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Inter connection and rising main with supply of specials of Augmentation of Biprodaspur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001355/2023-2024 | 4427/AD | 06/12/2023 | 01/10/2025 | BANGA NIRMAN | 11.91 | 0 | 0 | 80
11 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BIPRODASPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-GOSABA DISTRICT-SOUTH 24 PARGANAS | SM/13839 | New | Laying of additional pipe line and other allied works at Bipradaspur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000545/2024-2025 | 3716/AD | 12/09/2024 | 11/11/2024 | I.S. ENTERPRISE | 76.62 | 0 | 0 | 0
Total | [13 empty] | 659.9 | 0 | 0