## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Battali W/S Scheme , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001402/2022-2023 | 10927/AD | 06/02/2023 | 23/03/2023 | ARBINA ENTERPRISE | 8.57 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Battali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Gosaba] | Assistant Engineer | Junior Engineer | ORD/000548/2022-2023 | 411/SMD | 16/02/2023 | 17/05/2023 | P.K. ENGINEERING | 19.27 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Battali New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001881/2022-2023 | 7523/AD | 28/11/2022 | 12/01/2023 | M/S R.DUTTA & CO. | 4.32 | 4.32 | 100 | 99
4 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 255/AD | 24/04/2023 | 24/04/2023 | Resource Division | 39.04 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Construction of boundary wall at Pump House No-2 for Ground water Based at Battali Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000740/2024-2025 | 4397/AD | 05/11/2024 | 05/12/2024 | SUBHO CONSTRUCTION | 14.36 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Construction of boundary wall at Head Work Site for Ground water Based at Battali Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000739/2024-2025 | 4396/AD | 05/11/2024 | 20/12/2024 | FIDERE MARINE SERVICES PVT. LTD. | 33.7 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Battali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000214/2023-2024 | 954/AD | 06/06/2023 | 10/08/2023 | SALMAN CONSTRUCTION | 43.94 | 32.7 | 74.42 | 100
8 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Material Requisition To Resource Division |  |  | RTOR000409/2023-2024 | 363/AD | 19/01/2024 | 19/01/2024 | Resource Division | 8.01 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Quotation for new service( power) connection at Batali PH-1 Water supply scheme under Gosaba block. Reference ID:-106748166, Application No :-1008091231 |  |  | BILL/01841/2024-2025 | BP-2024-25-469 | 18/11/2024 | 18/11/2024 | WBSEDCL | 6.72 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Inter connection and rising main with supply of specials of Augmentation of Battali W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000125/2023-2024 | 571/AD | 15/05/2023 | 01/10/2025 | ARFIN CONSTRUCTION | 11.53 | 0 | 0 | 80
11 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Construction of OHR (150 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the BATTALI, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC= 1300] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000544/2023-2024 | 2210/AD | 10/08/2023 | 05/06/2024 | FIDERE MARINE SERVICES PVT. LTD. | 358.79 | 94.4 | 26.31 | 34
12 | SOUTH 24 PARGANAS | Gosaba | Alipore Division | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Battali W/S Scheme , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001401/2022-2023 | 10926/AD | 06/02/2023 | 01/11/2024 | ARBINA ENTERPRISE | 8.88 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Gosaba | S24 Pgns Mechanical | GROUND WATER BASED BATTALI PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : GOSABA, DISTRICT : SOUTH 24 PARGANAS | SM/13840 | New | Quotation for new service( power) connection at Battali PH-2 Water supply scheme under Gosaba block. Reference ID:-107071569, Application No :-1008591038 |  |  | BILL/00502/2025-2026 | 42151 | 01/08/2025 | 01/08/2025 | WBSEDCL | 4.77 | 0 | 0 | 0
Total | [13 empty] | 561.9 | 131.42 | 23.39