## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Ganeshnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/000424/2022-2023 | 3820/SMD | 29/12/2022 | 29/03/2023 | M.S.C ENTERPRISE | 19.27 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Ganeshnagar (Zone-I) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000422/2023-2024 | 1910/AD | 01/08/2023 | 31/08/2023 | MERAJUL ALAM | 19.95 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANESHNAGAR (ZONE-I) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001043/2022-2023 | 4156/AD | 19/08/2022 | 03/10/2022 | M/S R.DUTTA & CO. | 3.02 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ganeshnagar (Zone-I) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001303/2022-2023 | 9885/AD | 10/01/2023 | 24/02/2023 | MERAJUL ALAM | 38.59 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at 2nd Tubewell Site of Ganeshnagar Zone - I W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000317/2023-2024 | 193/KSD | 21/06/2023 | 28/06/2023 | FORTUNE ENGINEERING | 2.73 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Ganeshnagar Zone - I W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000316/2023-2024 | 191/KSD | 21/06/2023 | 28/06/2023 | FORTUNE ENGINEERING | 2.73 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Material Requisition To Resource Division |  |  | RTOR000131/2023-2024 | 667/AD | 17/05/2023 | 17/05/2023 | Resource Division | 6.31 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Material Requisition To Resource Division |  |  | RTOR000477/2023-2024 | 4782/AD | 19/12/2023 | 19/12/2023 | Resource Division | 14.38 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ganeshnagar (Zone-I) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1092] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000311/2023-2024 | 1517/AD | 15/07/2023 | 10/05/2024 | SUJAN KUMAR MISTRY | 242.27 | 0 | 0 | 30
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ganeshnagar Zone-I W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13842) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000413/2024-2025 | 3064/AD | 25/07/2024 | 08/09/2024 | LUCKY CONSTRUCTION (HASNABAD) | 28.53 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ganeshnagar Zone-I W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13842) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000592/2024-2025 | 4057/AD | 01/10/2024 | 31/10/2024 | AZAD RAHAMAN LASKAR | 8.68 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0 | 0 | 90
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13842 | New | Material Requisition To Resource Division |  |  | RTOR000784/2023-2024 | 628/AD | 30/01/2024 | 30/01/2024 | Resource Division | 0.62 | 0 | 0 | 0
Total | [13 empty] | 388.03 | 0 | 0