## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Gangapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000378/2022-2023 | 3782/SMD | 29/12/2022 | 29/03/2023 | SUBHRA ENTERPRISE | 18.5 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANGAPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001034/2022-2023 | 4153/AD | 19/08/2022 | 03/10/2022 | INDRANIL DUTTA & ASSOCIATES | 4.9 | 4.9 | 100 | 100
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 642/AD | 17/05/2023 | 17/05/2023 | Resource Division | 7.31 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Material Requisition To Resource Division |  |  | RTOR000500/2023-2024 | 4950/AD | 22/12/2023 | 22/12/2023 | Resource Division | 21.84 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gangapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002154/2023-2024 | 800/AD | 05/02/2024 | 05/04/2024 | M/S.SREEJIT ENTERPRISE | 33.05 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Allied works for pile and pile cap portion regarding the construction of 1 no. 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal & Laying distribution system for providing FHTC, Platform, Road Restoration and Y junction for Augmentation of Chhoto Banashyamnagar, Sibnagar, Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13835, SM/13844, SM/13843) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000338/2024-2025 | 2752/AD | 27/06/2024 | 24/02/2025 | M/S. S.S. ENTERPRISE | 373.95 | 75.61 | 20.22 | 20
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000207/2023-2024 | 790/AD | 24/05/2023 | 10/01/2025 | M/S. S.S. ENTERPRISE | 49.26 | 48.88 | 99.23 | 100
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Gangapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002074/2023-2024 | 770(A)/KSD | 08/12/2023 | 13/12/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Material Requisition To Resource Division |  |  | RTOR000954/2023-2024 | 1688/AD | 22/03/2024 | 22/03/2024 | Resource Division | 7.77 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Material Requisition To Resource Division |  |  | RTOR000749/2023-2024 | 584/AD | 29/01/2024 | 29/01/2024 | Resource Division | 1.31 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Payment for New Service connection of Gangapur PH-2, W/S Scheme Application No- 1007196380 Reference ID:- 106231315 |  |  | BILL/02231/2024-2025 | BP-2024-25-504 | 19/12/2024 | 19/12/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gangapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000122/2024-2025 | 2400/AD | 07/06/2024 | 04/03/2025 | PRADIP KUMAR MONDAL | 11.8 | 0 | 0 | 95
14 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Payment for New Service connection of Gangapur W/S Scheme PH-1 Application No- 1007196394 Reference ID:- 106231323 |  |  | BILL/02753/2024-2025 | BP-2024-25-567 | 17/02/2025 | 17/02/2025 | WBSEDCL | 4.7 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED GANGAPUR PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-PATHARPRATIMA DISTRICT-SOUTH 24 PARGANAS | SM/13843 | New | Construction of 150 cum. (3 nos.), 200 cum. (2 nos.), 250 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 10 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Choto Banashyamnagar, Sibnagar, Gangapur, Purba Sripatinagar, Paschim Sripatinagar, Uttar Surendraganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 9779] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000024/2023-2024 | 123/AD | 13/04/2023 | 26/01/2026 | M/S. S.S. ENTERPRISE | 2760.12 | 78.93 | 2.86 | 66
Total | [13 empty] | 3300.34 | 208.81 | 6.33