## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kedarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001059/2023-2024 | 3378/AD | 11/10/2023 | 25/11/2023 | DEBASIS JANA | 27.6 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KEDARPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000990/2022-2023 | 4151/AD | 19/08/2022 | 03/10/2022 | INDRANIL DUTTA & ASSOCIATES | 3.59 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 643/AD | 17/05/2023 | 17/05/2023 | Resource Division | 5.34 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Material Requisition To Resource Division |  |  | RTOR000496/2023-2024 | 4961/AD | 22/12/2023 | 22/12/2023 | Resource Division | 33.79 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03492/2023-2024 | BP-2023-24-378 | 13/11/2023 | 13/11/2023 | WBSEDCL | 2.47 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kedarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 972] | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_1, Kakdwip Sub Division | ORD/001879/2022-2023 | 12422/AD | 09/03/2023 | 03/01/2024 | FIDERE MARINE SERVICES PVT. LTD. | 284.95 | 0 | 0 | 25
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Kedarpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13845) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/000456/2024-2025 | 3414/AD | 21/08/2024 | 05/10/2024 | FIDERE MARINE SERVICES PVT. LTD. | 46.54 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kedarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/001310/2022-2023 | 9893/AD | 09/01/2023 | 23/02/2023 | MANDAL CONSTRUCTION | 38.6 | 0 | 0 | 90
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 of Kedarpur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/001907/2023-2024 | 1192/SMD | 22/03/2024 | 12/04/2024 | AHALYA ENGINEERING WORKS | 10.87 | 0 | 0 | 95
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Material Requisition To Resource Division |  |  | RTOR000751/2023-2024 | 586/AD | 29/01/2024 | 29/01/2024 | Resource Division | 0.96 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Material Requisition To Resource Division |  |  | RTOR000955/2023-2024 | 1689/AD | 22/03/2024 | 22/03/2024 | Resource Division | 0.47 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Payment for New Service connection Kedarpur PH-2 W/ S Scheme Application No:- 1007977598 Reference ID: 106692950 |  |  | BILL/01210/2024-2025 | BP-2024-25-256 | 12/08/2024 | 12/08/2024 | WBSEDCL | 2.48 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER SUPPLY SCHEME FOR KEDARPUR, UNDER ALIPORE DIVISION, BLOCK-PATHAR PRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/13845 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Kedarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000387/2022-2023 | 3790/SMD | 29/12/2022 | 24/06/2025 | AHALYA ENGINEERING WORKS | 18.75 | 0 | 0 | 40
Total | [13 empty] | 477.36 | 0 | 0