## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Uttar Kashiabad W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001162/2023-2024 | 3724/AD | 03/11/2023 | 03/12/2023 | KHATEJA CONSTRUCTION | 9.5 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Uttar Kashiabad W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001311/2022-2023 | 9894/AD | 10/01/2023 | 24/02/2023 | BENGAL ENTERPRISE | 38.58 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Uttar Kashiabad PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000912/2023-2024 | 270(I)/KSD | 10/07/2023 | 14/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( UTTAR KASHIABAD PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001050/2022-2023 | 3677/AD | 01/08/2022 | 15/09/2022 | LEMNISCATE | 4.84 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 658/AD | 17/05/2023 | 17/05/2023 | Resource Division | 8.96 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Material Requisition To Resource Division |  |  | RTOR000450/2023-2024 | 4715/AD | 18/12/2023 | 18/12/2023 | Resource Division | 38.71 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03417/2023-2024 | BP-2023-24-376 | 13/11/2023 | 13/11/2023 | WBSEDCL | 6.17 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Uttar Kashiabad W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001161/2023-2024 | 3723/AD | 03/11/2023 | 18/12/2023 | M/S MALI ENTERPRISE | 27.74 | 0 | 0 | 60
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Material Requisition To Resource Division |  |  | RTOR000814/2023-2024 | 659/AD | 30/01/2024 | 30/01/2024 | Resource Division | 1.61 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 01/04/2025 | GARGO TRADERS | 2798.35 | 0 | 0 | 64
12 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED UTTAR KASHIABAD PIPE WATER SUPPLY SCHEME BLOCK KAKDWIP UNDER ALIPORE DIVISION DISTRICT SOUTH 24 PARGANAS | SM/13846 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Uttar Kasiabad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000438/2022-2023 | 3834/SMD | 29/12/2022 | 12/10/2025 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 19.05 | 0 | 0 | 15
Total | [13 empty] | 2954.95 | 0 | 0