## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Rajrajeshwarpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000386/2022-2023 | 3789/SMD | 29/12/2022 | 29/03/2023 | T.S. CONSTRUCTION | 18.5 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAJRAJESHWARPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000988/2022-2023 | 4149/AD | 19/08/2022 | 03/10/2022 | INDRANIL DUTTA & ASSOCIATES | 4.58 | 4.58 | 100 | 100
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Rajrajeshwarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000932/2023-2024 | 276(I)/KSD | 13/07/2023 | 17/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 647/AD | 17/05/2023 | 17/05/2023 | Resource Division | 4.6 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Material Requisition To Resource Division |  |  | RTOR000483/2023-2024 | 4755/AD | 19/12/2023 | 19/12/2023 | Resource Division | 12.71 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Rajrajeshwarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001744/2022-2023 | 11559/AD | 17/02/2023 | 18/05/2023 | M/S ASCON | 99.44 | 92.1 | 92.62 | 90
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Rajrajeshwarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002158/2023-2024 | 803/AD | 05/02/2024 | 05/04/2024 | M/S ASCON | 26.34 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Raj Rajeshwarpur PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13868) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000396/2024-2025 | 4287/AD | 29/10/2024 | 28/12/2024 | M/S B.M. CONSTRUCTION | 97.23 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at P.H. 1&2, of Rajrajeshwarpur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000361/2024-2025 | 2664/SMD | 29/08/2024 | 27/11/2024 | T.S. CONSTRUCTION | 17.44 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Additional / Alternation Work of Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2 Zone-II for Augmentation Paschim Surendranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000001/2024-2025 | 1440/SMD | 18/04/2024 | 17/07/2024 | M/S. S.D.CONSTRUCTION | 17.3 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Rajrajeshwarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000123/2024-2025 | 2401/AD | 07/06/2024 | 07/07/2024 | SHIBSANKAR KAMILA | 9.6 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.95 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Material Requisition To Resource Division |  |  | RTOR000576/2023-2024 | 60/AD | 03/01/2024 | 03/01/2024 | Resource Division | 0.8 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Material Requisition To Resource Division |  |  | RTOR000753/2023-2024 | 588/AD | 29/01/2024 | 29/01/2024 | Resource Division | 3.08 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Material Requisition To Resource Division |  |  | RTOR000957/2023-2024 | 1691/AD | 22/03/2024 | 22/03/2024 | Resource Division | 13.68 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Rajrajeshwarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 838] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002067/2022-2023 | 13006/AD | 23/03/2023 | 31/05/2025 | M/S B.M. CONSTRUCTION | 263.39 | 57.77 | 21.93 | 30
17 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary etc at Rajrajeswarpur PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13868) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000236/2024-2025 | 2611/AD | 19/06/2024 | 21/10/2025 | M/S ASCON | 15.81 | 0 | 0 | 80
18 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAJRAJESHWARPUR, BLOCK PATHARPRATIMA DISTRICT SOUTH 24 PARGANAS UNDER ALIPORE DIVISION | SM/13868 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Rajrajeshwarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13868) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000076/2025-2026 | 2307/AD | 16/05/2025 | 30/06/2025 | B.K. ENTERPRISE. | 40.78 | 0 | 0 | 0
Total | [13 empty] | 646.72 | 154.94 | 23.96