## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DAKSHIN LAKHINARAYANPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000986/2022-2023 | 4148/AD | 19/08/2022 | 03/10/2022 | INDRANIL DUTTA & ASSOCIATES | 4.24 | 4.24 | 100 | 100
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 549/AD | 12/05/2023 | 12/05/2023 | Resource Division | 8.49 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Material Requisition To Resource Division |  |  | RTOR000504/2023-2024 | 4947/AD | 22/12/2023 | 22/12/2023 | Resource Division | 38.43 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.94 | 0.16 | 16.66 | 100
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Lakhinarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002620/2023-2024 | 731(A)/KSD | 05/12/2023 | 15/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Material Requisition To Resource Division |  |  | RTOR000754/2023-2024 | 589/AD | 29/01/2024 | 29/01/2024 | Resource Division | 1.52 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Dakshin Laxminarayanpur PH-2Water supply scheme Application No- 1007545287 Reference ID- 106480850 |  |  | BILL/02033/2024-2025 | BP-2024-25-491 | 09/12/2024 | 09/12/2024 | WBSEDCL | 4.81 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Dakshin Lakshminarayanpur PH-1 Water supply scheme Application No- 1008101139 Reference ID- 106755052 |  |  | BILL/02032/2024-2025 | BP-2024-25-490 | 09/12/2024 | 09/12/2024 | WBSEDCL | 10.26 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Lakhinarayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000379/2022-2023 | 3783/SMD | 29/12/2022 | 29/09/2025 | MAA TARA CONSTRUCTION | 19.28 | 0 | 0 | 90
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Lakhinarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000383/2023-2024 | 1776/AD | 26/07/2023 | 17/03/2025 | AQUATECH ENGINEERS | 89.3 | 49.45 | 55.37 | 68
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Dakshin Lakhinarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 600] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000619/2023-2024 | 3730/AD | 03/11/2023 | 16/06/2025 | SYN DEVELOPERS PVT. LTD. | 250.67 | 91.32 | 36.43 | 30
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Laksinarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002044/2023-2024 | 526/AD | 25/01/2024 | 14/09/2025 | SARADA CONSTRUCTION | 27.89 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Laksinarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002045/2023-2024 | 527/AD | 25/01/2024 | 25/01/2026 | GHOSH CONSTRUCTION | 9.6 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Lakhinarayanpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000209/2023-2024 | 860/AD | 27/05/2023 | 04/12/2024 | DEVAM ENTERPRISE | 38.28 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Improvement of outdoor illumination arrangement with allied works at PH No-2 of Dakshin Laxminarayanpur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/13869) | Assistant Engineer -II | Junior Engineer | ORD/000729/2025-2026 | 302-AE-II/SMD | 16/05/2025 | 06/06/2025 | MAA TARA CONSTRUCTION | 0.81 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DAKSHIN LAKHINARAYANPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13869 | New | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Dakshin Laxminarayanpur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. (SM/13869) | Assistant Engineer -II | Junior Engineer | ORD/000730/2025-2026 | 301-AE-II/SMD | 16/05/2025 | 06/06/2025 | MAA TARA CONSTRUCTION | 0.81 | 0 | 0 | 100
Total | [13 empty] | 505.81 | 145.65 | 28.79