## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2022 to 30.11.2023 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001754/2022-2023 | 561/KSD | 02/12/2022 | 30/11/2023 | NAMITA PRADHAN | 4.79 | 4.39 | 91.51 | 95
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DHABLAT (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001058/2022-2023 | 4649/AD | 06/09/2022 | 21/10/2022 | VOYAGER | 6.21 | 6.21 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001861/2022-2023 | 12414/AD | 09/03/2023 | 29/03/2025 | UCON (II) | 221.19 | 64.86 | 29.32 | 72
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I for Augmentation of Dhablahat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000794/2022-2023 | 281/SMD | 01/02/2023 | 29/06/2025 | GLACIER ENGINEERING CO. | 19.61 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC after completion of FHTC work for 01 Year for Augmentation of Dhablat (Zone- I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000402/2023-2024 | 1901/AD | 01/08/2023 | 30/09/2023 | SUDIP PRADHAN | 62.64 | 14.86 | 23.72 | 95
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2023 to 29.02.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002530/2023-2024 | 712/KSD | 30/11/2023 | 29/02/2024 | NAMITA PRADHAN | 1.2 | 1.15 | 96.08 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dhablat (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000972/2023-2024 | 321/KSD | 27/07/2023 | 31/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001281/2022-2023 | 9594/AD | 03/01/2023 | 17/02/2023 | SARADA CONSTRUCTION | 49.18 | 45.53 | 92.58 | 90
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Making and fixing of permanent display board at headwork site of Dhablat Zone - I & II, Kamalpur Rudranagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002164/2023-2024 | 951/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0.81 | 99.98 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000512/2023-2024 | 4830/AD | 20/12/2023 | 20/12/2023 | Resource Division | 23.39 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000335/2023-2024 | 3150/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Continuation order for the work of Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC after completion of FHTC work for 01 Year for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002452/2023-2024 | 1310/AD | 04/03/2024 | 18/04/2024 | SUDIP PRADHAN | 0 | 0 | NAN | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Continuation order for the work of Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002468/2023-2024 | 1361/AD | 06/03/2024 | 05/05/2024 | UCON | 0 | 0 | NAN | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.06.2024 to 31.08.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000672/2024-2025 | 984/KSD | 27/05/2024 | 27/08/2024 | NAMITA PRADHAN | 1.2 | 1.18 | 98 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Repairing of 1 no. Pump House, boundary wall, earth filling, approach road at 2nd Tubewell site for Dhablat W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002119/2024-2025 | 1968/KSD | 23/12/2024 | 12/01/2025 | KHOKAN MONDAL | 2.55 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Construction of Household Tap Platform at different household, fitting fixing supplying different dia. specials for Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000150/2024-2025 | 2488/AD | 14/06/2024 | 13/08/2024 | UCON (II) | 31.23 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.03.2024 to 31.05.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/003037/2023-2024 | 411/KSD | 27/02/2024 | 29/05/2024 | NAMITA PRADHAN | 1.2 | 1.16 | 96.48 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000673/2024-2025 | 1252/KSD | 28/08/2024 | 27/11/2024 | NAMITA PRADHAN | 1.2 | 0.37 | 30.7 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Construction of Household Tap Platform etc. at different household for Augmentation of Dhablat (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/13876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000149/2024-2025 | 2487/AD | 14/06/2024 | 13/08/2024 | SUDIP PRADHAN | 36.92 | 0 | 0 | 96
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Laying distribution system for additional works for Augmentation of Dhablat (Zone- I & II)) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part - A) (SM/13876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000761/2024-2025 | 4444/AD | 06/11/2024 | 05/01/2025 | SUDIP PRADHAN | 25.81 | 0 | 0 | 96
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000425/2024-2025 | 3204/AD | 01/08/2024 | 31/08/2024 | UCON | 5.36 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Repairing of 1 no. Pump House, boundary wall, earth filling & approach road at 1st Tubewell site for Dhablat W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002118/2024-2025 | 1967/KSD | 23/12/2024 | 12/01/2025 | KHOKAN MONDAL | 2.66 | 0 | 0 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Continuation order for Carriage of Chlorine from Ganeshpur store to different pump house of different PWSS of Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/003234/2023-2024 | 380/KSD | 21/02/2024 | 20/02/2025 | SUDIP PRADHAN | 2.39 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Dhablat (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001986/2023-2024 | 505/AD | 25/01/2024 | 24/02/2024 | M/S. MOYNA ENTERPRISE | 11.53 | 10.66 | 92.39 | 100
25 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dhablat (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001985/2023-2024 | 504/AD | 25/01/2024 | 10/03/2024 | SUDIP PRADHAN | 33.16 | 32.62 | 98.37 | 80
26 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I, PH-2 of Dhablat Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] (SM/13876) | Assistant Engineer -II | Junior Engineer | ORD/002378/2024-2025 | 1346/AE-II/SMD | 14/11/2024 | 29/11/2024 | GLACIER ENGINEERING CO. | 0.84 | 0 | 0 | 100
27 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I, PH-1 of Dhablat Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] (SM/13876) | Assistant Engineer -II | Junior Engineer | ORD/002379/2024-2025 | 1345/AE-II/SMD | 14/11/2024 | 29/11/2024 | GLACIER ENGINEERING CO. | 0.84 | 0 | 0 | 100
28 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000687/2023-2024 | 457/AD | 24/01/2024 | 24/01/2024 | Resource Division | 5.88 | 0 | 0 | 0
29 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000971/2023-2024 | 1764/AD | 27/03/2024 | 27/03/2024 | Resource Division | 1.41 | 0 | 0 | 0
30 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000532/2023-2024 | 16/AD | 02/01/2024 | 02/01/2024 | Resource Division | 3.97 | 0 | 0 | 0
31 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | Payment for New Service connection of Dhablat Augmentation W/S Scheme PH-2 Application No:- 1007672480 Reference ID:- 106558453 |  |  | BILL/00379/2024-2025 | BP-2024-25-89 | 05/06/2024 | 05/06/2024 | WBSEDCL | 8.35 | 0 | 0 | 0
32 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED DHABLAT (ZONE - I & II), PIPED WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13876 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05694/2023-2024 | BP-2023-24-644 | 29/03/2024 | 29/03/2024 | WBSEDCL | 4.71 | 0 | 0 | 0
Total | [13 empty] | 571 | 184.27 | 32.27