## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-III OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, | SM/13891 | Augmentation | Augmentation of laying distribution system at Zone-II & Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - IIIB / C) [No. of FHTC = 2650] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000043/2023-2024 | 178/AD | 19/04/2023 | 13/03/2025 | SUNNY ELECTRIC CO. | 146 | 16.88 | 11.56 | 20
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-III OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, | SM/13891 | Augmentation | Augmentation of laying distribution system at Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - III B) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000363/2023-2024 | 1564/AD | 17/07/2023 | 15/10/2023 | M/S SUBIR GHOSH | 524.53 | 371.44 | 70.81 | 84
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-III OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, | SM/13891 | Augmentation | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 1000 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-IIIA at Bhadura of Diamond Harbour -II Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002405/2023-2024 | 1153/AD | 27/02/2024 | 27/04/2024 | M/S. PROMILA CONSTRUCTION | 39.73 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-III OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, | SM/13891 | Augmentation | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-IIIB of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001530/2023-2024 | 435/DHSD | 22/09/2023 | 06/10/2023 | GEO SOLUTION | 0.84 | 0.84 | 100 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-III OF DIAMOND HARBOUR-II BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, | SM/13891 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000921/2023-2024 | 1263/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
Total | [13 empty] | 711.72 | 389.16 | 54.68