## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000365/2023-2024 | 3229/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000214/2023-2024 | 2023/AD | 05/08/2023 | 05/08/2023 | Resource Division | 14.51 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 1624/AD | 19/07/2023 | 19/07/2023 | Resource Division | 15.54 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-XI (Uttar Iswaripur, OHR Size-550) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/002102/2022-2023 | 343/DHSD | 18/11/2022 | 25/11/2022 | ASTER CONSULTANCY | 0.5 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000624/2023-2024 | 285/AD | 15/01/2024 | 15/01/2024 | Resource Division | 9.24 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000853/2023-2024 | 760/AD | 03/02/2024 | 03/02/2024 | Resource Division | 16.1 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XI at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-4113] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002066/2022-2023 | 12976/AD | 22/03/2023 | 07/09/2025 | ABDUL HAI | 463.63 | 0 | 0 | 20
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Land Development and beautification within the head works site under Zone No-XI of Kulpi Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000071/2025-2026 | 2260/AD | 14/05/2025 | 13/06/2025 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 19.56 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Laying of additional pipeline under the Augmentation Scheme of Zone-XI at Kulpi Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/13909] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000010/2025-2026 | 1621/AD | 03/04/2025 | 31/08/2025 | M/S. J.K. TRIPATHI & SONS | 120.58 | 0 | 0 | 10
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-XI OF KULPI BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/13909 | Augmentation | Restoration of W.B.M damaged due to laying of pipes from Raghunathpur more to Rajarampur F.P School under Kulpi Zone X under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000349/2025-2026 | 3130/AD | 03/07/2025 | 02/08/2025 | SAMIM AHMED | 11.64 | 0 | 0 | 100
Total | [13 empty] | 671.5 | 0 | 0