## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-XII OF KULPI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - MATHURAPUR, DISTRICT SOUTH 24 PARGANAS' | SM/13911 | Augmentation | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-XII of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001024/2022-2023 | 297/DHSD | 15/09/2022 | 15/10/2022 | GEO SOLUTION | 2.96 | 2.76 | 93.17 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-XII OF KULPI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - MATHURAPUR, DISTRICT SOUTH 24 PARGANAS' | SM/13911 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 12800/AD | 16/03/2023 | 16/03/2023 | Resource Division | 19.82 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-XII OF KULPI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - MATHURAPUR, DISTRICT SOUTH 24 PARGANAS' | SM/13911 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2022-2023 | 13/AD | 05/04/2023 | 05/04/2023 | Resource Division | 21 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-XII OF KULPI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - MATHURAPUR, DISTRICT SOUTH 24 PARGANAS' | SM/13911 | Augmentation | Additional laying of pipeline under the Augmentation Scheme of Kulpi Zone-XII under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001018/2024-2025 | 4929/AD | 03/12/2024 | 01/02/2025 | M/S. JHARNA ENTERPRISE | 77.72 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-XII OF KULPI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - MATHURAPUR, DISTRICT SOUTH 24 PARGANAS' | SM/13911 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000627/2023-2024 | 288/AD | 15/01/2024 | 15/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-XII OF KULPI BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA - MATHURAPUR, DISTRICT SOUTH 24 PARGANAS' | SM/13911 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000854/2023-2024 | 761/AD | 03/02/2024 | 03/02/2024 | Resource Division | 3.97 | 0 | 0 | 0
Total | [13 empty] | 137.79 | 2.76 | 2