## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA | SM/13952 | Augmentation | Construction of community tank in different Primary and High Schools under Zone-II of Falta Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000825/2022-2023 | 209/DHSD | 02/08/2022 | 16/09/2022 | B. MOOKHERJEE | 4.22 | 4.22 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA | SM/13952 | Augmentation | Extension of distribution pipeline at Chandpala Anantharampur & Brihaspatipur Mouza under Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001653/2021-2022 | 458/DHSD | 15/03/2022 | 30/03/2022 | PEECON | 3.72 | 3.72 | 99.97 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA | SM/13952 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000438/2023-2024 | 3623/AD | 30/10/2023 | 30/10/2023 | Resource Division | 12.32 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA | SM/13952 | Augmentation | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-II of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001536/2023-2024 | 437/DHSD | 22/09/2023 | 06/10/2023 | GEO SOLUTION | 0.84 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA | SM/13952 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000847/2023-2024 | 785/AD | 03/02/2024 | 03/02/2024 | Resource Division | 1.11 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA | SM/13952 | Augmentation | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-II of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 2180] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000264/2023-2024 | 3668/AD | 31/10/2023 | 18/01/2026 | PARAMESWAR CHOWDHURY | 271.31 | 251.69 | 92.77 | 95
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- II AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 PA | SM/13952 | Augmentation | Restoration and laying of parallel line by UPVC pipes in distribution system at Falta Zone-II for providing 100% FHTC within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Node Point- 223 to 224,305 to 299,249 to 290, 248 to 314, 314 to 335, 290 to 305, 305 to 312, 312 to 337, 337 to 339, 339 to 343, 343 to 345, 345 to 350) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001151/2023-2024 | 3197/AD | 04/10/2023 | 18/11/2023 | ADITYA HAZRA | 54.35 | 51.25 | 94.28 | 100
Total | [13 empty] | 347.87 | 310.88 | 89.37