## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kulpi | Alipore Division | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Ramanandapur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | SM/13962 | New | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Ramanandapur having village with maximum 100 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001127/2022-2023 | 8771/AD | 21/12/2022 | 19/02/2023 | JOY GURU TRADING | 32.55 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Kulpi | S24 Pgns Mechanical | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Ramanandapur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | SM/13962 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Ramanandapur Village of Ramnagar Gazipur Gram Panchyet Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kulpi] | Assistant Engineer -I | Junior Engineer | ORD/000610/2022-2023 | 763/SMD | 15/03/2023 | 13/06/2023 | M/S. SABITRI ENTERPRISE | 8.93 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kulpi | Alipore Division | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of Ramanandapur village of Ramnagar Gazipur Gram Panchayet in Kulpi Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | SM/13962 | New | Material Requisition To Resource Division |  |  | RTOR000874/2023-2024 | 781/AD | 03/02/2024 | 03/02/2024 | Resource Division | 0.65 | 0 | 0 | 0
Total | [13 empty] | 42.14 | 0 | 0