## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Continuation work order for Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001184/2023-2024 | 3945/AD | 17/11/2023 | 07/12/2023 | SARADA CONSTRUCTION | 24.59 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation Water Supply Scheme (SATYADASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Kakdwip Sub Division |  | ORD/001326/2022-2023 | 3309/AD | 20/07/2022 | 03/09/2022 | INDRANIL DUTTA & ASSOCIATES | 4.98 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | inking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001276/2022-2023 | 9588/AD | 03/01/2023 | 17/02/2023 | SARADA CONSTRUCTION | 49.18 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Satyadaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000638/2023-2024 | 2466/AD | 24/08/2023 | 22/11/2023 | PIKASU BOSE | 52.93 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Satyadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000934/2023-2024 | 277(I)/KSD | 13/07/2023 | 17/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Satyadaspur W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000998/2023-2024 | 505/KSD | 03/10/2023 | 10/10/2023 | FORTUNE ENGINEERING | 3.37 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 546/AD | 12/05/2023 | 12/05/2023 | Resource Division | 8.14 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Material Requisition To Resource Division |  |  | RTOR000296/2023-2024 | 3091/AD | 28/09/2023 | 28/09/2023 | Resource Division | 23.44 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03410/2023-2024 | BP-2023-24-375 | 13/11/2023 | 13/11/2023 | WBSEDCL | 10.4 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Satyadaspur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002040/2023-2024 | 522/AD | 25/01/2024 | 10/03/2024 | A.R.CONSTRUCTION | 33.21 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Sinking of 01 No. 250mm x 150mm dia. 450 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001979/2023-2024 | 438/AD | 24/01/2024 | 23/02/2024 | SARADA CONSTRUCTION | 30.53 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 & 2 of Satyadaspur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/001898/2023-2024 | 1183/SMD | 22/03/2024 | 12/04/2024 | S.K. ENTERPRISE | 21.68 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Material Requisition To Resource Division |  |  | RTOR000757/2023-2024 | 592/AD | 29/01/2024 | 29/01/2024 | Resource Division | 2.59 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Supply & delivery of Electrical accessories with allied items at PH No-2 of Satyadaspur W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/13965) | Assistant Engineer -II | Junior Engineer | ORD/000754/2025-2026 | 304-AE-II-SMD | 16/05/2025 | 06/06/2025 | S.K. ENTERPRISE | 0.55 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Supply & delivery of Electrical accessories with allied items at PH No-1 of Satyadaspur W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/13965) | Assistant Engineer -II | Junior Engineer | ORD/000755/2025-2026 | 303-AE-II-SMD | 16/05/2025 | 06/06/2025 | S.K. ENTERPRISE | 0.55 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Satyadaspur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000369/2022-2023 | 3773/SMD | 29/12/2022 | 01/04/2025 | S.K. ENTERPRISE | 19.67 | 0 | 0 | 30
18 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Satyadaspur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002152/2023-2024 | 799/AD | 05/02/2024 | 02/03/2025 | NARAYAN ENTERPRISE | 11.58 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SATYADASPUR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13965 | New | Construction of Approach Road with Box Culvert and Allied works at Satyadaspur Water Supply OHR Site, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13965) (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000902/2024-2025 | 4751/AD | 23/11/2024 | 24/05/2025 | PIKASU BOSE | 27.02 | 0 | 0 | 100
Total | [13 empty] | 325.72 | 0 | 0