## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000360/2023-2024 | 3224/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Additional balance works under the Augmentation scheme of Zone-IIIA at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001375/2024-2025 | 5520/AD | 28/12/2024 | 11/02/2025 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 35.51 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Zone-III of Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001923/2022-2023 | 12712/AD | 14/03/2023 | 12/06/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 138.23 | 99.86 | 72.24 | 70
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-III of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001537/2023-2024 | 438/DHSD | 22/09/2023 | 06/10/2023 | GEO SOLUTION | 0.84 | 0.37 | 44.2 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000926/2023-2024 | 1268/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000849/2023-2024 | 787/AD | 03/02/2024 | 03/02/2024 | Resource Division | 12.32 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Additional laying distribution system at Gazipur and Shibanipur Mouza for covering the command area of Falta Zone-III due to avoiding NH crossings of pipelines under Falta Zone-VII for providing 100% FHTC within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001974/2022-2023 | 12593/AD | 13/03/2023 | 18/12/2024 | JOY GURU TRADING | 28.35 | 15.77 | 55.62 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Balance works under the Augmentation scheme of Zone-IIIA at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001405/2024-2025 | 5545/AD | 30/12/2024 | 29/01/2025 | M/S B ENTERPRISE | 8.93 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Balance works under the Augmentation scheme of Zone-II at Falta block for providing balance pipe lying works, House Hold Tap connection, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000822/2024-2025 | 780/AD | 25/02/2025 | 08/10/2025 | M/S PARAMESWAR CHOWDHURY | 80.38 | 0 | 0 | 75
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- III AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/13969 | Augmentation | Restoration and Relaying of pipe line (damaged portion) by MS pipe in distribution system (Node Point- 3 to 5, 9 to 12, 12 to 13, 13 to 23) at Falta Zone-III within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000081/2025-2026 | 2422/AD | 23/05/2025 | 22/06/2025 | SRIJON ENTERPRISE | 6.15 | 0 | 0 | 0
Total | [13 empty] | 311.53 | 116 | 37.24