## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANESHNAGAR (ZONE-II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Kakdwip Sub Division |  | ORD/001341/2022-2023 | 3799/AD | 05/08/2022 | 19/09/2022 | M/S R.DUTTA & CO. | 3.69 | 3.69 | 100 | 100
2 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Ganeshnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000425/2022-2023 | 3821/SMD | 29/12/2022 | 01/04/2025 | S.K. ENTERPRISE | 19.67 | 3.98 | 20.25 | 30
3 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ganeshnagar (Zone-II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001304/2022-2023 | 9886/AD | 10/01/2023 | 24/02/2023 | IQBAL CONSTRUCTION | 38.59 | 21.68 | 56.17 | 0
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ganeshnagar (Zone-II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1366] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001546/2022-2023 | 11020/AD | 08/02/2023 | 05/12/2023 | SUJATA CONSTRUCTION | 313.36 | 143.88 | 45.92 | 65
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Ganeshnagar (Zone-II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000423/2023-2024 | 1911/AD | 01/08/2023 | 31/08/2023 | IQBAL CONSTRUCTION | 19.77 | 18.05 | 91.27 | 92
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at 2nd Tubewell Site of Ganeshnagar Zone - II W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000319/2023-2024 | 198/KSD | 23/06/2023 | 30/06/2023 | FORTUNE ENGINEERING | 2.73 | 2.73 | 100 | 100
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Ganeshnagar Zone - II W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000318/2023-2024 | 195/KSD | 22/06/2023 | 29/06/2023 | FORTUNE ENGINEERING | 2.73 | 2.73 | 100 | 100
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0.16 | 16.57 | 90
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Ganeshnagar Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002077/2023-2024 | 774(A)/KSD | 08/12/2023 | 13/12/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Material Requisition To Resource Division |  |  | RTOR000478/2023-2024 | 4782/AD | 19/12/2023 | 19/12/2023 | Resource Division | 22.81 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01118/2023-2024 | BP-2023-24-160 | 24/07/2023 | 24/07/2023 | WBSEDCL | 8.32 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ganeshnagar Zone-II W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13973) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000414/2024-2025 | 3065/AD | 25/07/2024 | 08/09/2024 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 28.86 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ganeshnagar Zone-II W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13973) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000843/2024-2025 | 4578/AD | 15/11/2024 | 15/12/2024 | M/S DEB ENTERPRISE | 8.56 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Addditional work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 & 2 Zone-II of Ganeshnagar W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Namkhana] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/001895/2023-2024 | 1182/SMD | 22/03/2024 | 12/04/2024 | S.K. ENTERPRISE | 16.8 | 16.14 | 96.1 | 100
15 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Material Requisition To Resource Division |  |  | RTOR000557/2023-2024 | 45/AD | 03/01/2024 | 03/01/2024 | Resource Division | 8.11 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Material Requisition To Resource Division |  |  | RTOR000981/2023-2024 | 1774/AD | 27/03/2024 | 27/03/2024 | Resource Division | 1.41 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED GANESHNAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION BLOCK-NAMKHANA,DISTRICT-SOUTH 24 PARGANAS | SM/13973 | New | Supply & delivery of Electrical accessories with allied items at Zone-II PH No-1 of Ganeshnagar W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. (SM/13973) | Assistant Engineer -II | Junior Engineer | ORD/000751/2025-2026 | 307-AE-II-SMD | 16/05/2025 | 06/06/2025 | S.K. ENTERPRISE | 0.55 | 0 | 0 | 100
Total | [13 empty] | 497.41 | 213.53 | 42.93