## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Surendraganj water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000376/2022-2023 | 3780/SMD | 29/12/2022 | 12/07/2025 | R.N.S. TRADING | 19.48 | 0 | 0 | 45
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme [DAKSHIN SURENDRAGANJ PWSS] including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001329/2022-2023 | 3311/AD | 20/07/2022 | 03/09/2022 | INDRANIL DUTTA & ASSOCIATES | 5.53 | 5.53 | 100 | 100
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Dakshin Surendraganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1535] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001877/2022-2023 | 12420/AD | 09/03/2023 | 01/07/2026 | GROWING CONCERN | 432.44 | 310.78 | 71.87 | 85
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000962/2023-2024 | 285(I)/KSD | 18/07/2023 | 22/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Continuation work order for Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Surendraganj W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001087/2023-2024 | 3554/AD | 17/10/2023 | 16/11/2023 | SARADA CONSTRUCTION | 49.21 | 46.39 | 94.28 | 100
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0.4 | 49.99 | 100
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 649/AD | 17/05/2023 | 17/05/2023 | Resource Division | 8.43 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Material Requisition To Resource Division |  |  | RTOR000473/2023-2024 | 4758/AD | 19/12/2023 | 19/12/2023 | Resource Division | 21.21 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Material Requisition To Resource Division |  |  | RTOR000299/2023-2024 | 3094/AD | 28/09/2023 | 28/09/2023 | Resource Division | 18.61 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03494/2023-2024 | BP-2023-24-377 | 13/11/2023 | 13/11/2023 | WBSEDCL | 3.37 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03524/2023-2024 | BP-2023-24-387 | 23/11/2023 | 23/11/2023 | WBSEDCL | 3.36 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002165/2023-2024 | 808/AD | 05/02/2024 | 02/03/2025 | TANMAY ROY CHOWDHURY | 33.34 | 15.85 | 47.54 | 100
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002166/2023-2024 | 809/AD | 05/02/2024 | 30/01/2025 | TIYASHA ENTERPRISE | 11.73 | 9.29 | 79.15 | 100
14 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 of Dakshin Surendraganj W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/001903/2023-2024 | 1188/SMD | 22/03/2024 | 04/05/2025 | R.N.S. TRADING | 8.35 | 0 | 0 | 90
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Dakshin Surendraganj W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001843/2023-2024 | 131/AD | 05/01/2024 | 05/03/2024 | BIMALENDU GIRI | 36.15 | 31.49 | 87.12 | 100
16 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Surendraganj PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13974) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000184/2024-2025 | 2544/AD | 18/06/2024 | 01/09/2024 | GROWING CONCERN | 91.83 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Material Requisition To Resource Division |  |  | RTOR000680/2023-2024 | 446/AD | 24/01/2024 | 24/01/2024 | Resource Division | 5.13 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUD WATER BASED DAKSHIN SURENDRAGANJ PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS. | SM/13974 | New | Material Requisition To Resource Division |  |  | RTOR000758/2023-2024 | 593/AD | 29/01/2024 | 29/01/2024 | Resource Division | 1.52 | 0 | 0 | 0
Total | [13 empty] | 750.97 | 420.23 | 55.96