## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 217/AD | 21/04/2023 |  | Resource Division | 103.46 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Conducting route survey, design distribution network and preparation & submission of DPR for Bibir Abad New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001892/2022-2023 | 8036/AD | 02/12/2022 | 16/01/2023 | INDRANIL DUTTA & ASSOCIATES | 5.72 | 5.72 | 100 | 0
3 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Inter connection and rising main with supply of specials of Augmentation of Bibir Abad W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000136/2023-2024 | 691/AD | 18/05/2023 | 02/06/2023 | KANIKA CONSTRUCTION | 17.48 | 0 | 0 | 0
4 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04082/2023-2024 | BP-2023-24-418 | 16/12/2023 |  | WBSEDCL | 3.68 | 0 | 0 | 0
5 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04082/2023-2024 | BP-2023-24-418 | 16/12/2023 |  | WBSEDCL | 3.68 | 0 | 0 | 0
6 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002021/2022-2023 | 12104/AD | 28/02/2023 | 29/04/2023 | SNEHA CONSTRUCTION | 59.76 | 37.32 | 62.45 | 98
7 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Bibir Abad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 378/SMD | 15/02/2023 | 16/05/2023 | PADMA ENGINEERING CO. | 27.75 | 8.38 | 30.19 | 30
8 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 07/01/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
9 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001767/2022-2023 | 12040/AD | 27/02/2023 | 13/04/2023 | KRISHNA CONSTRUCTION | 7.07 | 3.14 | 44.37 | 98
10 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Quotation for new service( power) connection at Chelikati bibirabad PH-1 Water supply scheme under Canning-II block. Reference ID:-106554875, Application No :-1007635912 |  |  | BILL/00385/2024-2025 | BP-2024-25-100 | 10/06/2024 |  | WBSEDCL | 3.59 | 0 | 0 | null
11 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Quotation for new service( power) connection at Chelikati Bibirabad PH-2 Water supply scheme under Canning-II block. Reference ID:-106554882, Application No :-1007635920 |  |  | BILL/00406/2024-2025 | BP-2024-25-101 | 10/06/2024 |  | WBSEDCL | 4.48 | 0 | 0 | null
12 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Quotation for new service( power) connection at Chelikati Bibirabad PH-2 Water supply scheme under Canning-II block. Reference ID:-106554882, Application No :-1007635920 |  |  | BILL/00406/2024-2025 | BP-2024-25-101 | 10/06/2024 |  | WBSEDCL | 4.48 | 0 | 0 | null
13 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-IX) Mini piped water supply scheme adjacent Bibir Abad W/S Scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000590/2022-2023 | 651/SMD | 03/03/2023 | 01/06/2023 | S.B.ENTERPRISE | 8.84 | 1.91 | 21.59 | 95
14 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-XI) Mini piped water supply scheme adjacent of Bibir Abad W/S Scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000595/2022-2023 | 660/SMD | 06/03/2023 | 04/06/2023 | MOUMITA ENTERPRISE | 8.9 | 4.02 | 45.12 | 95
15 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for Bibir Abad, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1703] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000122/2023-2024 | 158/AD | 18/04/2023 | 17/07/2023 | NAUTAN DAS AND CO | 300.96 | 119.68 | 39.77 | 70
16 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001821/2022-2023 | 12336/AD | 06/03/2023 | 20/04/2023 | M/S ARIYAN ENTERPRISE | 7.1 | 0 | 0 | 98
17 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Supply & installation of LED board at P.H. No-3 of Bibir Abad water supply scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000101/2024-2025 | 524/SMSD | 26/04/2024 | 11/05/2024 | M/S POUSALI ENTERPRISE | 0.39 | 0.2 | 50 | 100
18 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Improvement of outdoor illumination arrangement with allied works at Chelikati Bibib Abad, PH-3, under Canning-II Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002789/2023-2024 | 160/SMSD | 05/02/2024 | 20/02/2024 | PADMA ENGINEERING CO. | 0.88 | 0.44 | 50 | 100
19 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | GROUND WATER BASED BIBIR ABAD PIPED WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, PHE DTE,BLOCK-CANNING-II, DISTRICT- SOUTH 24 PARGANAS | SM/13975 | New | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001766/2022-2023 | 12039/AD | 27/02/2023 | 13/04/2023 | GIRI ENTERPRISE (NEW) | 7.33 | 0 | 0 | 98
Total | [13 empty] | 3200.03 | 180.8 | 5.65