## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/13978 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GOBINDPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001342/2022-2023 | 3800/AD | 05/08/2022 | 19/09/2022 | LEMNISCATE | 0.6 | 0.6 | 100 | 100
2 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/13978 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Gobindapur Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000601/2022-2023 | 678/SMD | 10/03/2023 | 08/06/2023 | M/S. SABITRI ENTERPRISE | 8.93 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/13978 | New | Laying distribution system, construction of 01 no. pump house size 5.40mtr. x 3.60 mtr., Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution & FHTC for 1 year after completion of FHTC works for Gobindapur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001425/2023-2024 | 4604/AD | 14/12/2023 | 13/03/2024 | M/S. LOKNATH CONSTRUCTION | 62.37 | 0 | 0 | 40
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/13978 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gobindapur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/001314/2022-2023 | 9897/AD | 10/01/2023 | 09/02/2023 | M/S NAIYA & MAITY | 19.06 | 17.07 | 89.57 | 100
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/13978 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st Tubewell Site of Gobindapur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001160/2023-2024 | 3722/AD | 03/11/2023 | 03/12/2023 | NEPAL CHANDRA PRADHAN | 9.43 | 9.43 | 99.98 | 100
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR GOBINDPUR UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/13978 | New | Material Requisition To Resource Division |  |  | RTOR000589/2023-2024 | 88/AD | 03/01/2024 | 03/01/2024 | Resource Division | 1.57 | 0 | 0 | 0
Total | [13 empty] | 101.97 | 27.11 | 26.58