## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Budhakhali Zone-I (Part- II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001101/2022-2023 | 8436/AD | 15/12/2022 | 29/01/2023 | SARADA CONSTRUCTION | 36.64 | 33.11 | 90.38 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation (BUDAKHALI ZONE- I PWSS) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [Phase-I]. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001897/2021-2022 | 6921/AD | 28/03/2022 | 12/05/2022 | M/S R.DUTTA & CO. | 7.34 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Budhakhali Zone-I Part-II W/S Scheme, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000593/2023-2024 | 2350/AD | 18/08/2023 | 02/10/2023 | UCON | 36.01 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-I) W/S Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000109/2021-2022 | 1193/AD | 07/07/2021 | 05/09/2021 | ADITYA HAZRA | 75.75 | 21.53 | 28.42 | 93
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Sinking of 1 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using PVC Pipe and Pre-packed Resin Bonded Gravel at 2nd Tubewell Site of Budhakhali Zone-I Water Supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001580/2021-2022 | 6960/AD | 29/03/2022 | 28/04/2022 | SIMPLEX DRILLING CO. | 18.06 | 16.09 | 89.07 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Budhakhali [Zone-I] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001810/2022-2023 | 05/AD | 01/04/2022 | 16/05/2022 | M/S R.DUTTA & CO. | 7.34 | 7.34 | 100 | 95
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Budhakhali Zone-I (Part-II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000939/2023-2024 | 279(I)/KSD | 13/07/2023 | 17/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000488/2023-2024 | 4785/AD | 19/12/2023 | 19/12/2023 | Resource Division | 34.44 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01119/2023-2024 | BP-2023-24-158 | 24/07/2023 | 24/07/2023 | WBSEDCL | 6.68 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001100/2022-2023 | 8435/AD | 15/12/2022 | 14/01/2023 | DIPANKAR DUTTA | 20.66 | 14.51 | 70.2 | 60
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Budhakhali Zone-I (Part-I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001346/2022-2023 | 10101/AD | 17/01/2023 | 13/11/2023 | UCON | 328.79 | 85.68 | 26.06 | 30
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Budhakhali Zone-1 PWSS, Block -Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14041) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000500/2024-2025 | 3603/AD | 06/09/2024 | 20/11/2024 | UCON (II) | 92.85 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-2 of Budhakhali Aug (Part-I & II) W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/002970/2023-2024 | 1286-AE-I-SMD | 11/12/2023 | 26/12/2023 | DAS ENTERPRISE | 0.89 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001098/2022-2023 | 8433/AD | 15/12/2022 | 13/02/2023 | M/S. UMA CONSTRUCTION | 88.4 | 45.63 | 51.61 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0.31 | 33.28 | 90
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000552/2023-2024 | 40/AD | 03/01/2024 | 03/01/2024 | Resource Division | 5.64 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000907/2023-2024 | 895/AD | 07/02/2024 | 07/02/2024 | Resource Division | 1.57 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000785/2023-2024 | 629/AD | 30/01/2024 | 30/01/2024 | Resource Division | 1.36 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001097/2022-2023 | 8432/AD | 15/12/2022 | 13/02/2023 | B.N.C. CONSTRUCTION | 85.86 | 49.56 | 57.72 | 90
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I (Part-I&II) for Augmentation of Budhakhali water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000802/2022-2023 | 149/SMD | 16/01/2023 | 30/06/2025 | DAS ENTERPRISE | 19.63 | 8.91 | 45.4 | 45
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Repairing of 1 no. Pump House, boundary wall and approach road at 2nd Tubewell site for Budhakhali Zone - I (Part-1) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14041) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002185/2024-2025 | 2066/KSD | 28/12/2024 | 17/01/2025 | IMAGINEER VENTURES | 2.44 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Budhakhali Zone - I (Part - I & II) W/S Scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) (2nd Call) (SM/14041) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000499/2024-2025 | 3602/AD | 06/09/2024 | 21/10/2024 | M/S MALI ENTERPRISE | 27.79 | 0 | 0 | 50
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001099/2022-2023 | 8434/AD | 15/12/2022 | 16/08/2024 | GIRI ENTERPRISE | 88.01 | 66.61 | 75.68 | 95
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BUDAKHALI ZONE- I (PART - I & II) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/14041 | Augmentation | Repairing of 1 no. Pump House, boundary wall and approach road at 1st Tubewell site for Budhakhali Zone 1 Part 1 W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14041) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002184/2024-2025 | 2065/KSD | 28/12/2024 | 17/01/2025 | HARAKRISHNA KAMILA | 2.56 | 0 | 0 | 100
Total | [13 empty] | 990.16 | 349.76 | 35.32