## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1,2,3 &4 Zone-I for Augmentation Paschim Surendranagar water supply scheme under SMD, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000370/2022-2023 | 3774/SMD | 29/12/2022 | 29/03/2023 | COMBINE ENTERPRISES | 38.52 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Paschim Surendranagar (Zone-I) [Part-I, II & III] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001791/2022-2023 | 3186/AD | 15/07/2022 | 29/08/2022 | INDRANIL DUTTA & ASSOCIATES | 9.15 | 9.15 | 100 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Construction of 1 no. 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone-I (Part - I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part- III) [No. of FHTC = 286] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002028/2022-2023 | 12995/AD | 23/03/2023 | 28/07/2025 | DEEPAK ENTERPRISE | 248.99 | 42.5 | 17.07 | 40
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Construction of 2 nos. 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone-I (Part - I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part- I & II) [No. of FHTC = 160] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000348/2023-2024 | 1658/AD | 20/07/2023 | 15/05/2024 | BHUWALKA DEVELOPMENTS PVT LTD. | 541.96 | 289.89 | 53.49 | 50
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001205/2023-2024 | 4082/AD | 23/11/2023 | 07/01/2024 | BANGA NIRMAN | 27.91 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001206/2023-2024 | 4083/AD | 23/11/2023 | 23/12/2023 | M/S A.K. ENTERPRISE | 9.7 | 7.24 | 74.68 | 50
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001203/2023-2024 | 4080/AD | 23/11/2023 | 07/01/2024 | REZU CONSTRUCTION | 27.88 | 16.02 | 57.46 | 60
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Sinking of 04 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Paschim Surendranagar (Zone-I) (Part-I, II & III) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001275/2022-2023 | 9587/AD | 03/01/2023 | 03/04/2023 | MUNNA AGROTECH ENTERPRISE | 77.16 | 59.39 | 76.96 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Surging of 2 nos. Tubewell for augmentation of Paschim Surendranagar Zone-I W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000522/2023-2024 | 350/KSD | 09/08/2023 | 17/02/2025 | S.K.GOLUI | 2.73 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-I (Part - I, II & III) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000927/2023-2024 | 273(I)/KSD | 13/07/2023 | 17/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001204/2023-2024 | 4081/AD | 23/11/2023 | 01/04/2025 | B.B. CONSTRUCTION | 9.38 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0.47 | 49.99 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000456/2023-2024 | 4763/AD | 19/12/2023 | 19/12/2023 | Resource Division | 84.68 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Augmentation of Paschim Surendranagar Zone I Part I & II W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000440/2024-2025 | 3075/AD | 25/07/2024 | 23/09/2024 | CHHETRI ENTERPRISES | 74.62 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at P.H. 1,2,3 & 4 Zone-I for Augmentation Paschim Surendranagar W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/001929/2024-2025 | 1778/SMD | 29/05/2024 | 27/08/2024 | COMBINE ENTERPRISES | 33.95 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Repairing of Pump House and Boundary Wall with approach road at 1st Tubewell site for Paschim Surendranagar Zone-I (Part-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002096/2024-2025 | 1929/KSD | 20/12/2024 | 14/01/2025 | AJMIR ENTERPRISE | 4.08 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-I (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002608/2023-2024 | 294/KSD | 07/02/2024 | 12/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone - I (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002603/2023-2024 | 273/KSD | 02/02/2024 | 07/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Sinking of 01 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Paschim Surendranagar Zone-I W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000166/2024-2025 | 2517/AD | 15/06/2024 | 15/07/2024 | MUNNA AGROTECH ENTERPRISE | 20.39 | 18.01 | 88.33 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Repairing of Pump House and Boundary Wall with approach road at 2nd Tubewell site for Paschim Surendranagar Zone-I (Part-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001295/2024-2025 | 1930/KSD | 20/12/2024 | 14/01/2025 | ARUP GAYEN | 4.18 | 3.52 | 84.21 | 100
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at P.H. 1 & 2, of Uttar Surendraganj W/S Schemes i.c.w Aug of Paschim Surendranagar (Zone-I) (Part-I,II & III) , pipe water supply scheme Phase- B under South 24-Pgs Mechanical Division, PHE Dte. [Block-Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/001933/2024-2025 | 1777/SMD | 29/05/2024 | 01/10/2025 | NUPUR CHANDRA HALDER | 17.24 | 0 | 0 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000567/2023-2024 | 80/AD | 03/01/2024 | 03/01/2024 | Resource Division | 2.65 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000960/2023-2024 | 1694/AD | 22/03/2024 | 22/03/2024 | Resource Division | 3.69 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000760/2023-2024 | 595/AD | 29/01/2024 | 29/01/2024 | Resource Division | 3.71 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Payment for New Service connection of Paschim Surendranagar PH-2 Zone-I ( Part-I) W/S Scheme Application No- 1007513394 Reference ID:- 1064600085 |  |  | BILL/00210/2024-2025 | BP-2024-25-70 | 16/05/2024 | 16/05/2024 | WBSEDCL | 4.03 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Payment for New Service connection of Paschim Surendranagar Zone-I ( Part-III) W/S Scheme PH-1 Application No:- 1007513529 Reference ID:- 106460084 |  |  | BILL/00962/2024-2025 | BP-2024-25-187 | 19/07/2024 | 19/07/2024 | WBSEDCL | 3.42 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Payment for New Service connection of Paschim Surendranagar PH-2, Zone-I ( Part-III) W/S Scheme Application No:- 1007513563 Reference ID:- 106460079 |  |  | BILL/00963/2024-2025 | BP-2024-25-188 | 19/07/2024 | 19/07/2024 | WBSEDCL | 6.66 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PASCHIM SURENDRANAGAR (ZONE-I) (PART I, II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/14124 | Augmentation | Payment for New Service connection of Paschim Surendranagar PH-1 Zone-I ( Part-I) W/S Scheme Paschim Surendranagar Application No- 1007513251 Reference ID:- 106460080 |  |  | BILL/00209/2024-2025 | BP-2024-25-70 | 16/05/2024 | 16/05/2024 | WBSEDCL | 8.88 | 0 | 0 | 0
Total | [13 empty] | 1267.96 | 447.66 | 35.31