## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1200] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002076/2022-2023 | 12946/AD | 21/03/2023 | 19/06/2023 | SARADA CONSTRUCTION | 151.76 | 145.68 | 95.99 | 77
2 | SOUTH 24 PARGANAS | Namkhana | S24 Pgns Mechanical | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Amrabati water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/000805/2022-2023 | 268/SMD | 31/01/2023 | 01/05/2023 | CINZANO | 32.26 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Amrabati PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001784/2022-2023 | 3693/AD | 02/08/2022 | 16/09/2022 | M/S R.DUTTA & CO. | 9.01 | 9.01 | 100 | 95
4 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Amarabati W/S Scheme, Namkhana Block, Dist. - South 24 Parganas, under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000588/2023-2024 | 2345/AD | 18/08/2023 | 02/10/2023 | SARADA CONSTRUCTION | 42.65 | 39.14 | 91.77 | 98
5 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000938/2023-2024 | 278(I)/KSD | 13/07/2023 | 17/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
6 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Material Requisition To Resource Division |  |  | RTOR000484/2023-2024 | 4786/AD | 19/12/2023 | 19/12/2023 | Resource Division | 64.94 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 100] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002075/2022-2023 | 12945/AD | 21/03/2023 | 15/01/2024 | SARADA CONSTRUCTION | 169.37 | 100.96 | 59.61 | 28
8 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1200] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002077/2022-2023 | 12947/AD | 21/03/2023 | 19/06/2023 | SARADA CONSTRUCTION | 169.36 | 136.85 | 80.81 | 24
9 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.63 | 0.16 | 24.95 | 100
10 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Road restoration and other allied works for laying pipe line to providing Functional Household Tap Connection (FHTC) to all households for Aamarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002565/2023-2024 | 510/KSD | 15/03/2024 | 20/03/2024 | SARADA CONSTRUCTION | 3.63 | 3.6 | 99.28 | 90
11 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Material Requisition To Resource Division |  |  | RTOR000554/2023-2024 | 42/AD | 03/01/2024 | 03/01/2024 | Resource Division | 16.45 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Material Requisition To Resource Division |  |  | RTOR000983/2023-2024 | 1776/AD | 27/03/2024 | 27/03/2024 | Resource Division | 4.9 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000501/2024-2025 | 3604/AD | 06/09/2024 | 01/09/2025 | SARADA CONSTRUCTION | 80.76 | 0 | 0 | 55
14 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Repairing of Pump House and Boundary wall at 1st Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002125/2024-2025 | 1972/KSD | 23/12/2024 | 12/01/2025 | IMAGINEER VENTURES | 1.88 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Repairing of Pump House and Boundary wall at 2nd Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002126/2024-2025 | 1973/KSD | 23/12/2024 | 12/01/2025 | FORTUNE ENGINEERING | 1.87 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Namkhana | Alipore Division | GROUND WATER BASED AMRABATI PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-NAMKHANA,DISTRICT - SOUTH 24 PARGANAS | SM/14156 | New | Repairing of Pump House and Boundary wall at 3rd Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002133/2024-2025 | 1974/KSD | 23/12/2024 | 12/01/2025 | FORTUNE ENGINEERING | 1.33 | 0 | 0 | 0
Total | [13 empty] | 751.29 | 435.89 | 58.02