## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Harwood Point water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000806/2022-2023 | 269/SMD | 31/01/2023 | 01/05/2023 | M/S. DILIP MITRA | 33.71 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Harwood Point W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000958/2023-2024 | 2990/AD | 26/09/2023 | 26/10/2023 | FORTUNE ENGINEERING | 9.53 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Hardwood Point PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/001783/2022-2023 | 3692/AD | 02/08/2022 | 16/09/2022 | LEMNISCATE | 8.62 | 0 | 0 | 95
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 661/AD | 17/05/2023 | 17/05/2023 | Resource Division | 19.45 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Material Requisition To Resource Division |  |  | RTOR000455/2023-2024 | 4719/AD | 18/12/2023 | 18/12/2023 | Resource Division | 89.99 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Harwood Point W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000399/2024-2025 | 3182/AD | 31/07/2024 | 30/08/2024 | M/S D.D. INFRASTRUCTURE | 9.03 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Harwood Point W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000957/2023-2024 | 2989/AD | 26/09/2023 | 10/11/2023 | M/S SAMADDAR CONSTRUCTION | 27.68 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 450 cum. capacity OHR of Hardwood Point PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002066/2023-2024 | 761(A)/KSD | 08/12/2023 | 13/12/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Material Requisition To Resource Division |  |  | RTOR000994/2023-2024 | 1787/AD | 27/03/2024 | 27/03/2024 | Resource Division | 6.44 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Material Requisition To Resource Division |  |  | RTOR000816/2023-2024 | 661/AD | 30/01/2024 | 30/01/2024 | Resource Division | 3.49 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Release of fund to PWD towards road restoration work. |  |  | BILL/00939/2024-2025 | BP-2024-25-438 | 09/08/2024 | 09/08/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 31.01 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Hardwood Point Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 2040] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001864/2022-2023 | 12417/AD | 09/03/2023 | 17/04/2026 | M/S SAMADDAR CONSTRUCTION | 167.97 | 0 | 0 | 50
14 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction of 450 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Hardwood Point Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1500 ] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002029/2022-2023 | 12996/AD | 23/03/2023 | 05/07/2026 | M/S SAMADDAR CONSTRUCTION | 366.95 | 0 | 0 | 50
15 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Hardwood Point PWSS, Block -Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14157) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000334/2024-2025 | 2739/AD | 26/06/2024 | 25/08/2024 | M/S SAMADDAR CONSTRUCTION | 138.26 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Harwood Point W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14157) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/003052/2024-2025 | 4087/AD | 03/10/2024 | 02/03/2025 | GARAI INFRA PROJECT | 19.96 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Continuation Work Order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Harwood Point W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001152/2024-2025 | 2863/AD | 06/07/2024 | 31/07/2024 | SHREE J M CONSTRUCTION | 20.39 | 0 | 0 | 100
Total | [13 empty] | 953.89 | 0 | 0