## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Harwood Point water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000806/2022-2023 | 269/SMD | 31/01/2023 | 01/05/2023 | M/S. DILIP MITRA | 33.71 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Harwood Point W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000958/2023-2024 | 2990/AD | 26/09/2023 | 26/10/2023 | FORTUNE ENGINEERING | 9.53 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Hardwood Point PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/001783/2022-2023 | 3692/AD | 02/08/2022 | 16/09/2022 | LEMNISCATE | 8.62 | 8.62 | 100 | 95
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 661/AD | 17/05/2023 | 17/05/2023 | Resource Division | 19.45 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Material Requisition To Resource Division |  |  | RTOR000455/2023-2024 | 4719/AD | 18/12/2023 | 18/12/2023 | Resource Division | 89.99 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Harwood Point W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000399/2024-2025 | 3182/AD | 31/07/2024 | 30/08/2024 | M/S D.D. INFRASTRUCTURE | 9.03 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Harwood Point W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000957/2023-2024 | 2989/AD | 26/09/2023 | 10/11/2023 | M/S SAMADDAR CONSTRUCTION | 27.68 | 8.84 | 31.95 | 100
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 450 cum. capacity OHR of Hardwood Point PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002066/2023-2024 | 761(A)/KSD | 08/12/2023 | 13/12/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
10 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Material Requisition To Resource Division |  |  | RTOR000994/2023-2024 | 1787/AD | 27/03/2024 | 27/03/2024 | Resource Division | 6.44 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Material Requisition To Resource Division |  |  | RTOR000816/2023-2024 | 661/AD | 30/01/2024 | 30/01/2024 | Resource Division | 3.49 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Release of fund to PWD towards road restoration work. |  |  | BILL/00939/2024-2025 | BP-2024-25-438 | 09/08/2024 | 09/08/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 31.01 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Hardwood Point PWSS, Block -Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14157) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000334/2024-2025 | 2739/AD | 26/06/2024 | 02/05/2025 | M/S SAMADDAR CONSTRUCTION | 138.26 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Harwood Point W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14157) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/003052/2024-2025 | 4087/AD | 03/10/2024 | 02/03/2025 | GARAI INFRA PROJECT | 19.96 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARDWOOD POINT PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK-KAKDWIP,DISTRICT - SOUTH 24 PARGANAS | SM/14157 | New | Continuation Work Order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Harwood Point W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001152/2024-2025 | 2863/AD | 06/07/2024 | 31/07/2024 | SHREE J M CONSTRUCTION | 20.39 | 0 | 0 | 100
Total | [13 empty] | 418.97 | 17.95 | 4.28