## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Haradhanpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000072/2023-2024 | 53/KSD | 28/04/2023 | 02/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Haradhanpur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001324/2022-2023 | 9246/AD | 29/12/2022 | 12/02/2023 | SIMPLEX DRILLING CO. | 45.85 | 27.63 | 60.26 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Haradhanpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001786/2022-2023 | 3185/AD | 15/07/2022 | 29/08/2022 | VOYAGER | 7.42 | 7.42 | 100 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Haradhanpur (Zone-II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000585/2023-2024 | 2342/AD | 18/08/2023 | 02/10/2023 | UNIQUE AGENCY (PARTNER) | 39.91 | 32.37 | 81.1 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Haradhanpur (Zone-II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000713/2023-2024 | 2534/AD | 28/08/2023 | 27/09/2023 | UNIQUE AGENCY (PARTNER) | 5.05 | 5.05 | 100 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000499/2023-2024 | 4825/AD | 20/12/2023 | 20/12/2023 | Resource Division | 16.05 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000293/2023-2024 | 3089/AD | 28/09/2023 | 28/09/2023 | Resource Division | 1.15 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000329/2023-2024 | 3144/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02640/2023-2024 | BP-2023-24-276 | 03/10/2023 | 03/10/2023 | WBSEDCL | 5.05 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Continuation order for the work of Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 480] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002464/2023-2024 | 1341/AD | 05/03/2024 | 04/05/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 0 | 0 | NAN | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 480] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001858/2022-2023 | 12411/AD | 09/03/2023 | 07/06/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 265.34 | 235.77 | 88.86 | 90
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Haradhanpur (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002178/2023-2024 | 814/AD | 05/02/2024 | 06/03/2024 | M/S. NIRODAMAYEE ENTERPRISE | 11.83 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-1 Haradhanpur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] | Assistant Engineer -I | Junior Engineer | ORD/002867/2023-2024 | 525/AE-I/SMD | 15/03/2024 | 30/03/2024 | M.D ENTERPRISE | 0.9 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Laying distribution system for additional works of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) (SM/14159) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000555/2024-2025 | 3784/AD | 18/09/2024 | 02/11/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 12.13 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Construction of Household Tap Platform at different household for Augmentation of Haradhanpur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (for Zone-I) (SM/14159) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000145/2024-2025 | 2483/AD | 14/06/2024 | 28/08/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 65.9 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site for Haradhanpur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001477/2023-2024 | 4686/AD | 18/12/2023 | 17/01/2024 | SIMPLEX DRILLING CO. | 24.97 | 22.47 | 90.01 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Making and fixing of permanent display board at headwork site of Haradhanpur Zone - I & II, Nagendraganj Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002156/2023-2024 | 949/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0.4 | 49.99 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Haradhanpur (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002282/2023-2024 | 918/AD | 08/02/2024 | 08/04/2024 | KHOKAN MONDAL | 33.69 | 33 | 97.93 | 100
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Supply & delivery of submersible pumping machinery for PH-I, Zone-I of Augmentation of Haradhanpur W/S Scheme under South 24pgs Mechanical Division, PHE, Dte. (Block- Sagar) | Assistant Engineer -I | Junior Engineer | ORD/002035/2023-2024 | 1226-AE-I-SMD | 04/12/2023 | 19/12/2023 | M.D ENTERPRISE | 0.94 | 0.94 | 100 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000541/2023-2024 | 25/AD | 02/01/2024 | 02/01/2024 | Resource Division | 5.7 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000689/2023-2024 | 459/AD | 24/01/2024 | 24/01/2024 | Resource Division | 8.24 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Payment for New Service connection Haradhanpur Augmentation Z-I PH-1 W/S Scheme Application No:- 1007177572 Reference ID: 106218967 |  |  | BILL/01209/2024-2025 | BP-2024-25-255 | 12/08/2024 | 12/08/2024 | WBSEDCL | 4.42 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 816] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001856/2022-2023 | 12410/AD | 09/03/2023 | 02/07/2025 | UNIQUE AGENCY (PARTNER) | 367.4 | 323.38 | 88.02 | 98
24 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED HARADHANPUR (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14159 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I for Augmentation of Haradhanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000350/2022-2023 | 3754/SMD | 29/12/2022 | 29/03/2023 | M.D ENTERPRISE | 22.37 | 10.11 | 45.19 | 5
Total | [13 empty] | 945.89 | 699.02 | 73.9