## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar, Zone -II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001404/2022-2023 | 10334/AD | 25/01/2023 | 24/02/2023 | A.S.A.CONSTRUCTION AND CONSULTANT | 16.68 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 534AD | 12/05/2023 | 12/05/2023 | Resource Division | 14.88 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Material Requisition To Resource Division |  |  | RTOR000521/2023-2024 | 4937/AD | 22/12/2023 | 22/12/2023 | Resource Division | 22.61 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Improvement of outdoor illumination arrangement with allied works at Zone-II, PH-1 of Madhabnagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I | Junior Engineer | ORD/002868/2023-2024 | 1228/AE-I/SMD | 04/12/2023 | 19/12/2023 | JOYSHREE CONCERN | 0.89 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Madhabnagar (Zone-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001781/2022-2023 | 11758/AD | 21/02/2023 | 07/04/2023 | S. CHAKRABORTY AND CO. | 36.7 | 0 | 0 | 90
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Madhabnagar Zone-II W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000917/2023-2024 | 2970/AD | 26/09/2023 | 10/11/2023 | AALOKRENU | 27.45 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Continuation work order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Madhabnagar (Zone-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) |  | Juniour Engineer_4, Kakdwip Sub Division | ORD/002295/2023-2024 | 216/AD | 11/01/2024 | 10/02/2024 | S. CHAKRABORTY AND CO. | 20.41 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Madhabnagar Zone-II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002605/2023-2024 | 291/KSD | 07/02/2024 | 12/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Material Requisition To Resource Division |  |  | RTOR000581/2023-2024 | 56/AD | 03/01/2024 | 03/01/2024 | Resource Division | 2.57 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Material Requisition To Resource Division |  |  | RTOR000946/2023-2024 | 1680/AD | 22/03/2024 | 22/03/2024 | Resource Division | 28.55 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Madhabnagar PH-2 Water supply scheme Application No- 1007193395 Reference ID- 106229290 |  |  | BILL/02034/2024-2025 | BP-2024-25-487 | 09/12/2024 | 09/12/2024 | WBSEDCL | 3.64 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Madhabnagar Zone - II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001403/2022-2023 | 10333/AD | 25/01/2023 | 30/03/2025 | A.K. SIKDAR | 61.73 | 0 | 0 | 75
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Madhabnagar Zone-II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000204/2023-2024 | 742/AD | 23/05/2023 | 16/02/2025 | REALIENCE CONSTRUCTION | 507.58 | 0 | 0 | 40
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Madhabnagar Zone-II W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000154/2023-2024 | 676/AD | 17/05/2023 | 16/06/2023 | DEY ENTERPRISE (III) | 9.62 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-II of Madhabnagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000391/2022-2023 | 3793/SMD | 29/12/2022 | 29/09/2025 | JOYSHREE CONCERN | 26.01 | 0 | 0 | 40
17 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar Zone -II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =820] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001756/2022-2023 | 11756/AD | 21/02/2023 | 21/06/2025 | DIPAK ROY | 156.91 | 0 | 0 | 70
18 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | MADHABNAGAR ZONE-II PIPED WATER SUPPLY SCHEME IN PATHAR PRATIMA BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER JAL JEEVAN MISSION UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE. | SM/14462 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Indraprastha W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13804) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002528/2024-2025 | 813/AD | 27/02/2025 | 13/04/2025 | CHANDA ENTERPRISE (KOLKATA) | 40.78 | 0 | 0 | 0
Total | [13 empty] | 978.45 | 0 | 0