## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRIC | SM/14463 | Augmentation | Augmentation of laying distribution system to extend the benefit of 100% household by providing Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-V of Diamond Harbour-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. (Phase-II) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001393/2022-2023 | 10865/AD | 04/02/2023 | 05/05/2023 | TIRUPATI ENTERPRISES | 298.7 | 0 | 0 | 85
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRIC | SM/14463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000883/2023-2024 | 757/AD | 03/02/2024 | 03/02/2024 | Resource Division | 11.24 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRIC | SM/14463 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000923/2023-2024 | 1265/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRIC | SM/14463 | Augmentation | Road restoration under Diamond Harbour II Block Bituminous Road and concrete road for the old pipe laying work under Zone-IV & V (Sarisha GP) under the jurisdiction of PWD and Diamond Harbour II Panchayat Samiti / Block under Jal Jeevan Mission within Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000015/2025-2026 | 1929/AD | 23/04/2025 | 07/06/2025 | SRINAGAR COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED | 5 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT DIAMOND HARBOUR _II WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRIC | SM/14463 | Augmentation | Road restoration under Diamond Harbour II Block Bituminous Road and concrete road for the old pipe laying work under Zone-V (Kalatolahut GP) under the jurisdiction of PWD and Diamond Harbour II Panchayat Samiti / Block under Jal Jeevan Mission within Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000016/2025-2026 | 1930/AD | 23/04/2025 | 22/06/2025 | SRIJON ENTERPRISE | 24.22 | 0 | 0 | 100
Total | [13 empty] | 339.78 | 0 | 0