## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sudhanshupur piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1167] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000294/2023-2024 | 1504/AD | 15/07/2023 | 10/05/2024 | SARDAR ENTERPRISE | 488.97 | 95.16 | 19.46 | 30
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Sudhansupur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000490/2023-2024 | 1791/AD | 26/07/2023 | 25/08/2023 | M/S MODINA ENTERPRISE | 15.27 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Survey, Design and DPR preparation for Augmentation of ground water based Sudhanshupur Water Supply Scheme to accommodate FHTC in Gosaba Block of South 24 Parganas District under Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/002065/2022-2023 | 1470/CSD | 28/03/2023 | 12/04/2023 | TECH VISION | 3.84 | 3.76 | 97.8 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 249/AD | 24/04/2023 | 24/04/2023 | Resource Division | 32.05 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 1056/AD | 15/06/2023 | 15/06/2023 | Resource Division | 7.19 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | : Construction of boundary wall at Head Work site for Augmentation of Sudhansupur Piped Water Supply Scheme, Block- Gosaba under Canning Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000734/2024-2025 | 4392/AD | 05/11/2024 | 05/12/2024 | SARDAR ENTERPRISE | 29.93 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Gosaba) Name of PWSS :- Purba Radhanagar (Zone - I), Purba Radhanagar (Zone - II), Purba Radhanagar (Zone - III), Satjelia (Zone - I), Satjelia (Zone - II), Satjelia (Zone - III), Sudhansupur, Sadhupur (Zone-I), Sadhupur (Zone-II), Kachukhali, Harishpur (Zone- I) & Harishpur (Zone- II) (For 16 (Sixteen) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000970/2024-2025 | 1183/CSD | 24/10/2024 | 13/11/2024 | SURYA ENTERPRISE | 4.68 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05699/2023-2024 | BP-2023-24-609 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Renovation and retrofitting of Pump House No. 2 of Augmentation of Sudhansupur W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000184/2025-2026 | 547/CSD | 30/04/2025 | 30/05/2025 | MOHANA ENTERPRISES | 3.63 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Renovation and retrofitting of Pump House No. 1 of Augmentation of Sudhansupur W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000188/2025-2026 | 608/CSD | 16/05/2025 | 15/06/2025 | MOHANA ENTERPRISES | 4.29 | 0 | 0 | 100
Total | [13 empty] | 593.12 | 98.92 | 16.68