## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Sudhansupur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000490/2023-2024 | 1791/AD | 26/07/2023 | 25/08/2023 | M/S MODINA ENTERPRISE | 15.27 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Survey, Design and DPR preparation for Augmentation of ground water based Sudhanshupur Water Supply Scheme to accommodate FHTC in Gosaba Block of South 24 Parganas District under Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/002065/2022-2023 | 1470/CSD | 28/03/2023 | 12/04/2023 | TECH VISION | 3.84 | 0 | 0 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 249/AD | 24/04/2023 | 24/04/2023 | Resource Division | 32.05 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 1056/AD | 15/06/2023 | 15/06/2023 | Resource Division | 7.19 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sudhanshupur piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1167] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000294/2023-2024 | 1504/AD | 15/07/2023 | 10/05/2024 | SARDAR ENTERPRISE | 488.97 | 0 | 0 | 30
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | : Construction of boundary wall at Head Work site for Augmentation of Sudhansupur Piped Water Supply Scheme, Block- Gosaba under Canning Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000734/2024-2025 | 4392/AD | 05/11/2024 | 05/12/2024 | SARDAR ENTERPRISE | 29.93 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF SUDHANSUPUR PIPED WATER SUPPLY SCHEME, BLOCK-GOSABA,DISTRICT-SOUTH 24 PARGANAS | SM/14466 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05699/2023-2024 | BP-2023-24-609 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
Total | [13 empty] | 580.53 | 0 | 0