## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | SM/14468 | Augmentation | Augmentation of laying distribution system including construction of 400 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000021/2023-2024 | 92/AD | 11/04/2023 | 05/02/2024 | BIDYUT UDYOG | 196.04 | 0 | 0 | 1
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | SM/14468 | Augmentation | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- VII at Falta block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte.(Phase-II). [No of FHTC-1300]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002051/2022-2023 | 12973/AD | 22/03/2023 | 20/06/2023 | SUPRITI ENTERPRISE | 106.69 | 59.72 | 55.98 | 70
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | SM/14468 | Augmentation | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-VIII of Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No of FHTC-700]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000013/2023-2024 | 04/AD | 04/04/2023 | 03/07/2023 | TANMAY ROY CHOWDHURY | 169.17 | 99.02 | 58.53 | 80
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | SM/14468 | Augmentation | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(B) at Falta block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000304/2023-2024 | 1507/AD | 15/07/2023 | 27/10/2026 | SUBRATA GHOSH | 285.95 | 29.8 | 10.42 | 40
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | SM/14468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000135/2022-2023 | 22/AD | 05/04/2023 | 05/04/2023 | Resource Division | 101.08 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | SM/14468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 1277/AD | 05/07/2023 | 05/07/2023 | Resource Division | 101.08 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | SM/14468 | Augmentation | Payment for "Restoration of Fatepur Falta Road (MDR) (various chainage 465.5 mtr. , damaged caused due to laying of water pipelines by PHED under Diamond Harbour Sub Division in the District of South 24 Pgs" - Vide memo no. 1347(W)/681G, dated 02.11.2023 of Superintending Engineer, Southern Circle, P.W.Dte., |  |  | BILL/01189/2024-2025 | BP-2024-25-559 | 11/09/2024 | 11/09/2024 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DEPTT. | 28 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION IN DISTRIBUTION SYSTEM WITH CONSTRUCTION OF OHR AND ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FHTC UNDER ZONE-VIII OF FALTA BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT SOU | SM/14468 | Augmentation | Payment for "Restoration of Fatepur Falta Road (MDR) near Panchloki to Basulat Battala, damaged caused due to laying of water pipelines by PHED under Diamond Harbour Sub Division in the District of South 24 Pgs" - Vide memo no. 1347(W)/681G, dated 02.11.2023 of Superintending Engineer, Southern Circle, P.W.Dte. |  |  | BILL/01188/2024-2025 | BP-2024-25-558 | 11/09/2024 | 11/09/2024 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DEPTT. | 0.94 | 0 | 0 | 0
Total | [13 empty] | 988.95 | 188.54 | 19.06