## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/14473 | Augmentation | Augmentation of laying distribution system including construction of 400 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000021/2023-2024 | 92/AD | 11/04/2023 | 05/02/2024 | BIDYUT UDYOG | 196.04 | 0 | 0 | 1
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/14473 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000241/2023-2024 | 2780/AD | 12/09/2023 | 12/09/2023 | Resource Division | 15.19 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/14473 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000620/2023-2024 | 281/AD | 15/01/2024 | 15/01/2024 | Resource Division | 9.06 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/14473 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000930/2023-2024 | 1272/AD | 02/03/2024 | 02/03/2024 | Resource Division | 1.24 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/14473 | Augmentation | Additional balance works under the Augmentation scheme of Zone-VIII at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001378/2024-2025 | 5523/AD | 28/12/2024 | 07/05/2026 | MONDAL ENTERPRISE (MURSHIDABAD) | 44.51 | 0 | 0 | 75
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/14473 | Augmentation | Balance works under the Augmentation scheme of Zone-VIII at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001407/2024-2025 | 5552/AD | 30/12/2024 | 13/02/2025 | TANMAY ROY CHOWDHURY | 31.11 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/14473 | Augmentation | Construction of approach WBM Road for Falta Zone-VIIIB OHR site within Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001022/2024-2025 | 4933/AD | 03/12/2024 | 26/06/2026 | SUBRATA GHOSH | 14.19 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VIII AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH | SM/14473 | Augmentation | Land Development and beautification within the head works site under Zone-VIIIB at Falta block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000070/2025-2026 | 2259/AD | 14/05/2025 | 09/04/2026 | SUBRATA GHOSH | 19.47 | 0 | 0 | 0
Total | [13 empty] | 330.8 | 0 | 0