## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Sinking of 01(One) no.100mm x 50mm dia. having 5 nos. Strainer upto 300 mtr (Average) depth at office of the Assistant Engineer, Diamond Harbour Sub-Division under Zone-VII of Diamond Harbour-I Block under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001158/2023-2024 | 527/DHSD | 13/10/2023 | 20/10/2023 | M/S B ENTERPRISE | 2.51 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 33/AD | 05/04/2023 | 05/04/2023 | Resource Division | 2.3 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000132/2022-2023 | 24/AD | 05/04/2023 | 05/04/2023 | Resource Division | 16.27 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000240/2023-2024 | 2653/AD | 04/09/2023 | 04/09/2023 | Resource Division | 30.8 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000425/2023-2024 | 3611/AD | 30/10/2023 | 30/10/2023 | Resource Division | 15.4 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000235/2023-2024 | 2196/AD | 10/08/2023 | 10/08/2023 | Resource Division | 37.76 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Construction of Car parking shed by Galvanised corrugated iron sheet at office premiese under Zone VII of Diamond Harbour-I Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas"under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001123/2023-2024 | 518/DHSD | 13/10/2023 | 12/11/2023 | M/S B ENTERPRISE | 4.8 | 4.75 | 98.89 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000916/2023-2024 | 1258/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.93 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VII at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 5140] | Assistant Engineer, Diamond Harbour sub division,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/001398/2022-2023 | 10870/AD | 04/02/2023 | 21/10/2025 | AVIK ENTERPRISE | 383.98 | 352.26 | 91.74 | 95
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-VII of Diamond Harbour-I Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002025/2022-2023 | 12929/AD | 21/03/2023 | 05/04/2023 | AVIK ENTERPRISE | 10.47 | 3.2 | 30.55 | 90
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Additional laying of UPVC pipe line for balance portion in the distribution system for coverage 100% FHTC in Zone-VII at Diamond Harbour- I block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002116/2023-2024 | 830/AD | 05/02/2024 | 21/03/2024 | AVIK ENTERPRISE | 23.85 | 23.52 | 98.63 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | Additional balance works under the Augmentation scheme of Zone-VII at Diamond Harbour-I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2 DHSD | ORD/000080/2025-2026 | 2421/AD | 23/05/2025 | 22/07/2025 | AVIK ENTERPRISE | 87.23 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE-VII OF DIAMOND HARBOUR-I BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA | SM/14474 | Augmentation | R.C.C Roof construction over existing Laboratory building of Office of the Assistant Engineer, Diamond Harbour Sub Division, PHE Dte. under Zone VII of Diamond Harbour-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001146/2023-2024 | 524/DHSD | 13/10/2023 | 12/11/2023 | SAMIM AHMED | 4.81 | 0 | 0 | 100
Total | [13 empty] | 621.11 | 383.73 | 61.78