## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IV at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 2510] | Assistant Engineer, Diamond Harbour sub division,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/001397/2022-2023 | 10869/AD | 04/02/2023 | 23/07/2025 | PROJECT & MAINTENANCE | 197.45 | 76.07 | 38.52 | 80
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (period from 01/05/2023 to 31/10/2023) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000081/2023-2024 | 27/DHSD | 25/04/2023 | 26/10/2023 | SUMAN HALDER | 2.4 | 2.24 | 93.37 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Hiring of an Inspection Vehicle for the use of JJM related works under the office of the Assistant Engineer, Diamond Harbour Sub-Division, under Alipore Division, P.H.E. Dte. (period from 01/10/2023 to 30/09/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 3 DHSD | ORD/001268/2023-2024 | 449/DHSD | 29/09/2023 | 29/09/2024 | M.P. ENTERPRISE (II) | 4.8 | 2.38 | 49.66 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2022-2023 | 23/AD | 05/04/2023 | 05/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000347/2023-2024 | 3211/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000233/2023-2024 | 2194/AD | 10/08/2023 | 10/08/2023 | Resource Division | 15.42 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000913/2023-2024 | 1255/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000892/2023-2024 | 746/AD | 03/02/2024 | 03/02/2024 | Resource Division | 15.46 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FROM DISTRIBUTION SYSTEM WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLD AT ZONE - IV OF DIAMOND HARBOUR-I BLOCK WITHIN MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- | SM/14475 | Augmentation | Laying of distribution pipe line of different dia. M.S. and different dia. UPVC pipe line of damage portion due to road widening for 5 nos. culvert crossing with allied works at sonamukhi bridge near Parulia G.P, at Dostipur-Usthi road, at Hatuganje more to Netra stations road and OHR head work site to Hatuganje more road under Augmentation scheme of Diamond Harbour-I Zone-IV, Zone-X & Zone-III within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2 DHSD | ORD/000098/2025-2026 | 2527/AD | 30/05/2025 | 29/07/2025 | SRIJON ENTERPRISE | 89.87 | 0 | 0 | 100
Total | [13 empty] | 327.61 | 80.69 | 24.63