## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 | SM/14477 | Augmentation | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-V of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001540/2023-2024 | 439/DHSD | 22/09/2023 | 06/10/2023 | GEO SOLUTION | 0.84 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 | SM/14477 | Augmentation | Trial Run of existing distribution system (CI/DI/UPVC/HDPE) for Falta Zone-V under Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000818/2024-2025 | 4502/AD | 11/11/2024 | 11/12/2024 | K.P. CONSTRUCTION | 7.55 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 | SM/14477 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000928/2023-2024 | 1270/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 | SM/14477 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000850/2023-2024 | 788/AD | 03/02/2024 | 03/02/2024 | Resource Division | 13.43 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 | SM/14477 | Augmentation | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-V of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 1500] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001391/2022-2023 | 10863/AD | 04/02/2023 | 30/03/2025 | CONCORD ENGINEERING | 230.24 | 95.06 | 41.29 | 55
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 | SM/14477 | Augmentation | Balance works under the Augmentation scheme of Zone-V at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002256/2024-2025 | 568/AD | 12/02/2025 | 09/11/2025 | SAB ENGINEERING WORKS | 29.99 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- V AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 24 | SM/14477 | Augmentation | Laying of additional UPVC pipe line for balance portion in the distribution system for Providing balance FHTC to cover 100% household under the Augmentation Scheme of Falta Zone-V within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/002403/2023-2024 | 1152/AD | 27/02/2024 | 23/12/2024 | S.M. ENTERPRISE | 29.8 | 23.56 | 79.07 | 90
Total | [13 empty] | 312.46 | 118.62 | 37.96