## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Manasadwip Zone-I & Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000079/2023-2024 | 63/KSD | 02/05/2023 | 06/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-U) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001469/2023-2024 | 4699/AD | 18/12/2023 | 17/01/2024 | M/S BIJALI ENTERPRISE | 15.38 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying UPVC pipe line between Nodal Point 226 to 227 and 227 to 229 of Manasadwip Water supply scheme under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000444/2020-2021 | 830/KSD | 16/10/2020 | 30/11/2020 | PIKASU BOSE | 3.55 | 3.55 | 99.96 | 5
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Manasadwip [Zone-I & II] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001916/2021-2022 | 6554/AD | 10/03/2022 | 24/04/2022 | VOYAGER | 9.82 | 9.82 | 100 | 95
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system and retrofitting of Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001422/2022-2023 | 10980/AD | 07/02/2023 | 09/03/2023 | ANANDA MAITY | 12.91 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000503/2023-2024 | 4827/AD | 20/12/2023 | 20/12/2023 | Resource Division | 36.98 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000326/2023-2024 | 3141/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.6 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03669/2023-2024 | BP-2023-24-391 | 23/11/2023 | 23/11/2023 | WBSEDCL | 8.76 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001824/2022-2023 | 12120/AD | 01/03/2023 | 25/06/2026 | BENGAL BUILDERS | 449.37 | 177.16 | 39.42 | 34
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Manasadwip water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000345/2022-2023 | 3749/SMD | 29/12/2022 | 29/03/2023 | ASHUTOSH DAS & CO. | 22.32 | 10.08 | 45.18 | 45
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Manasadwip Zone-II W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000591/2023-2024 | 2348/AD | 18/08/2023 | 02/10/2023 | BENGAL BUILDERS | 49.7 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Construction of Household Tap Platform, Valve Chamber etc. at different household for Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14518) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000136/2024-2025 | 2474/AD | 14/06/2024 | 13/08/2024 | SWAPAN KUMAR PRADHAN | 67.89 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 5th Tubewell Site for Augmentation of Manasadwip (Zone I & II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000139/2024-2025 | 2477/AD | 14/06/2024 | 14/07/2024 | M/S. PARAMESWAR ENTERPRISE | 11.66 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002533/2023-2024 | 259/KSD | 31/01/2024 | 31/07/2024 | BADSHA ALOM | 2.4 | 0 | 0 | 10
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Manasadwip Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002626/2023-2024 | 887/KSD | 16/12/2023 | 26/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system and retrofitting of Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001544/2022-2023 | 10981/AD | 07/02/2023 | 09/03/2023 | M/S MAA BASANTI ENTERPRISE | 9.62 | 9.59 | 99.67 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Manasadwip (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001545/2022-2023 | 10982/AD | 07/02/2023 | 24/03/2023 | SIMPLEX DRILLING CO. | 45.85 | 44.47 | 97 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-H) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001464/2023-2024 | 4695/AD | 18/12/2023 | 17/01/2024 | KAMALA ENTERPRISE (I) | 5.78 | 5.73 | 99.12 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001689/2023-2024 | 5115/AD | 29/12/2023 | 27/02/2024 | SHYAM DEVELOPER | 44.93 | 11.74 | 26.12 | 80
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-K) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001692/2023-2024 | 5117/AD | 29/12/2023 | 28/01/2024 | MONDAL ENTERPRISE (JOYNAGAR) | 9.39 | 9.17 | 97.7 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001462/2023-2024 | 4693/AD | 18/12/2023 | 01/02/2024 | DIPA CHHETRI | 24.81 | 24.81 | 99.97 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-F) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001463/2023-2024 | 4694/AD | 18/12/2023 | 17/01/2024 | P.N. ENTERPRISE | 6.42 | 6.36 | 98.98 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-J) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001466/2023-2024 | 4697/AD | 18/12/2023 | 17/01/2024 | SRI DURGA ENTERPRISE | 5.48 | 5.44 | 99.35 | 100
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001465/2023-2024 | 4696/AD | 18/12/2023 | 17/01/2024 | S.B. ENTERPRISE | 5.65 | 5.6 | 99.07 | 100
25 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-T) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001467/2023-2024 | 4698/AD | 18/12/2023 | 17/01/2024 | AVIJIT MAITY | 9.41 | 9.29 | 98.7 | 100
26 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001461/2023-2024 | 4692/AD | 18/12/2023 | 01/02/2024 | M/S KHAJABABA ENTERPRISE | 29.61 | 29.59 | 99.93 | 100
27 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-M) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001783/2023-2024 | 920/KSD | 19/12/2023 | 18/01/2024 | M/S B.S. ENTERPRISE | 4.64 | 4.63 | 99.95 | 100
28 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Making and fixing of permanent display board at headwork site of Dhaspara Zone - I & II, Manasadwip Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002161/2023-2024 | 950/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.81 | 0.4 | 49.99 | 100
29 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-Q) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002432/2023-2024 | 367/KSD | 19/02/2024 | 20/03/2024 | M/S. MA BHABANI CONSTRUCTION | 3.81 | 3.8 | 99.86 | 100
30 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-R) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002433/2023-2024 | 368/KSD | 19/02/2024 | 20/03/2024 | S. DAS ENTERPRISE | 3.2 | 3.2 | 99.93 | 100
31 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-S) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002434/2023-2024 | 369/KSD | 19/02/2024 | 20/03/2024 | M/S MA KALI ELECTRIC LIGHT CORPORATION. | 3.01 | 2.99 | 99.3 | 100
32 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-L) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002430/2023-2024 | 365/KSD | 19/02/2024 | 20/03/2024 | M/S DHIRENDRA ENTERPRISE | 4.8 | 4.79 | 99.77 | 100
33 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-O) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002431/2023-2024 | 366/KSD | 19/02/2024 | 20/03/2024 | M/S S.M. CONSTRUCTION | 4.49 | 4.49 | 100 | 100
34 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Development of Land for sinking of 2 nos. big dia. tubewell at 1st & 2nd Tubewell Site for Augmentation of Manasadwip Zone-II W/S scheme under JJM, Block : Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002571/2023-2024 | 514/KSD | 15/03/2024 | 20/03/2024 | M/S KHAJABABA ENTERPRISE | 2.96 | 0.78 | 26.38 | 100
35 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Manasadwip (Zone-I and II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000137/2024-2025 | 2475/AD | 14/06/2024 | 29/07/2024 | SIMPLEX DRILLING CO. | 49.93 | 46.6 | 93.33 | 50
36 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000540/2023-2024 | 24/AD | 02/01/2024 | 02/01/2024 | Resource Division | 2.08 | 0 | 0 | 0
37 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000690/2023-2024 | 460/AD | 24/01/2024 | 24/01/2024 | Resource Division | 10.56 | 0 | 0 | 0
38 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000902/2023-2024 | 888/AD | 07/02/2024 | 07/02/2024 | Resource Division | 25 | 0 | 0 | 0
39 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Payment for New Service connection Manasadwip Zone-II PH-2 W/ S Scheme Application No:- 1008023799 Reference ID: 106715305 |  |  | BILL/01516/2024-2025 | BP-2024-25-362 | 11/09/2024 | 11/09/2024 | WBSEDCL | 5.27 | 0 | 0 | 0
40 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Repairing of Pump House and Boundary wall with construction of approach road at Head work site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002188/2024-2025 | 2069/KSD | 28/12/2024 | 17/01/2025 | P.N. ENTERPRISE | 4.15 | 0 | 0 | 0
41 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Repairing of Pump House and Boundary wall with approach road at 2nd Tubewell site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002189/2024-2025 | 2070/KSD | 28/12/2024 | 17/01/2025 | SWAPAN KUMAR PRADHAN | 2.89 | 0 | 0 | 0
42 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Providing support services for data mapping of available data within command area for preparation of GMIS at Manasadwip (Zone-I and II) (SM/13117) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000019/2025-2026 | 2005/AD | 28/04/2025 | 28/05/2025 | LEMNISCATE | 7.21 | 0 | 0 | 100
43 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-II, PH-1 of Manasadwip W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar][SM/14518] | Assistant Engineer -II | Junior Engineer | ORD/001891/2024-2025 | 954-AE-II-SMD | 31/07/2024 | 15/08/2024 | ASHUTOSH DAS & CO. | 0.91 | 0 | 0 | 0
44 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Repairing of Pump House and Boundary wall with approach road at 3rd Tubewell site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002190/2024-2025 | 2071/KSD | 28/12/2024 | 17/01/2025 | P.N. ENTERPRISE | 4.21 | 0 | 0 | 0
45 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001690/2023-2024 | 5116/AD | 29/12/2023 | 28/02/2025 | PALCON | 46.25 | 44.65 | 96.54 | 100
46 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Manasadwip (Zone I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001984/2023-2024 | 503/AD | 25/01/2024 | 01/04/2025 | M/S. PRADHAN ENTERPRISE | 11.64 | 0 | 0 | 100
47 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-G) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000381/2024-2025 | 3073/AD | 25/07/2024 | 31/07/2025 | MONCON INDIA | 6.12 | 0 | 0 | 100
48 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Construction of 2 nos. Pump House for 4th & 5th Tubewell site for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000140/2024-2025 | 2478/AD | 14/06/2024 | 11/04/2025 | M/S. BABA KAPIL MUNI ENTERPRISE | 14.28 | 0 | 0 | 100
49 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Manasadwip (Zone I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001983/2023-2024 | 502/AD | 25/01/2024 | 16/09/2025 | M/S RELIABLE ENTERPRISE | 33.08 | 0 | 0 | 60
50 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MANASADWIP (ZONE-I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/14518 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Augmentation of Manasadwip (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14518) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000371/2024-2025 | 2965/AD | 15/07/2024 | 30/04/2025 | BENGAL BUILDERS | 96.01 | 0 | 0 | 0
Total | [13 empty] | 1236.57 | 479.22 | 38.75