## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IV of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001001/2022-2023 | 284/DHSD | 13/09/2022 | 13/10/2022 | GEO SOLUTION | 3.72 | 3.49 | 93.71 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Investigation of soil for the proposed 1(one) no. R.C.C. Over Head Reservoir i.e. at Zone-IV (OHR Size-1250) of Falta Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000515/2022-2023 | 5536/AD. | 21/09/2022 | 01/10/2022 | RAJIB KUMAR CHAKRABORTY | 0.82 | 0.82 | 100 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 21/AD | 05/04/2023 | 05/04/2023 | Resource Division | 393.9 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000226/2023-2024 | 2189/AD | 10/08/2023 | 10/08/2023 | Resource Division | 37.76 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000362/2023-2024 | 3226/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000430/2023-2024 | 3624/AD | 30/10/2023 | 30/10/2023 | Resource Division | 36.96 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Augmentation of laying distribution system including construction of 1250 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IV at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8074]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/000350/2023-2024 | 1660/AD | 20/07/2023 | 28/05/2026 | S.MISRA INFRADEV PVT. LTD. | 1874.49 | 1422.21 | 75.87 | 87
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Laying of additional pipeline, road restoration works etc. under the Augmentation scheme of Zone-IV at Falta block for providing 100% FHTC under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/14680] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001305/2024-2025 | 5379/AD | 23/12/2024 | 08/03/2025 | S.MISRA INFRADEV PVT. LTD. | 152.39 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-IV (OHR Size-1250) of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/002103/2022-2023 | 344/DHSD | 18/11/2022 | 25/11/2022 | ASTER CONSULTANCY | 0.5 | 0.5 | 100 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000616/2023-2024 | 277/AD | 15/01/2024 | 15/01/2024 | Resource Division | 12.78 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000927/2023-2024 | 1269/AD | 02/03/2024 | 02/03/2024 | Resource Division | 2.48 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Payment against "Restoration of Fatepur Falta Road (MDR) 0.3Km-0.6Km, 9.539Km- 10.05, 13.728Km-14.098Km, 14.098Km-14.418Km, 12.683Km-13.728Km & 9nos points: 5.9-6.1Km) under Diamond Harbour Highway Division, PWD damaged caused due to laying of water pipe lines by PHED under Diamond Harbour Sub Division, PHE Dte. in the district of South 24 Pgs" vide Memo no. 1118(W)/618G, Dt. 01.08.2024 of SE, Southern highway Circle P.W.(Roads) Dte. & 9nos |  |  | BILL/01575/2024-2025 | BP-2024-25-890 | 19/11/2024 | 19/11/2024 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DTE. | 85.83 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Balance works under the Augmentation scheme of Zone-I at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002390/2024-2025 | 637/AD | 18/02/2025 | 04/04/2025 | M/S. S.S. ENTERPRISE | 23.13 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Balance works under the Augmentation scheme of Zone-V at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002256/2024-2025 | 568/AD | 12/02/2025 | 24/12/2025 | SAB ENGINEERING WORKS | 29.99 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Land Development and ICBP within the head works site under Zone-IV at Falta block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000815/2024-2025 | 4501/AD | 11/11/2024 | 10/01/2025 | S.MISRA INFRADEV PVT. LTD. | 25.1 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Construction of pipe carrying structure with laying of 100 mm dia. GI Distribution line for crossing of Canal at Kantafuli mouza (Node point 103 to 110) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000530/2024-2025 | 3647/AD | 09/09/2024 | 24/10/2024 | S.MISRA INFRADEV PVT. LTD. | 20.24 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Construction of pipe carrying structure with laying of 323.9 mm dia. (OD) M.S. and 100 mm dia. GI Distribution line for crossing of Bhatheria Canal at Gangadharpur mouza (Node point 297 to 299) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District. South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000529/2024-2025 | 3646/AD | 09/09/2024 | 24/10/2024 | S.MISRA INFRADEV PVT. LTD. | 38.41 | 8.14 | 21.19 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM INCLUDING OHR WITH ALLIED WORKS TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS BY PROVIDING FHTC UNDER ZONE-IV OF FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA-MATHURAPUR, DISTRICT-SOUTH 24 | SM/14680 | Augmentation | Construction of pipe carrying structure with laying of 273 mm dia (OD) MS Distribution line for crossing of Canal at Dholtikari mouza (Node point 10 to 11 ) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000531/2024-2025 | 3648/AD | 09/09/2024 | 24/10/2024 | S.MISRA INFRADEV PVT. LTD. | 23.17 | 9.09 | 39.24 | 100
Total | [13 empty] | 2761.87 | 1444.26 | 52.29