## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Re-layig of damaged distribution pipeline along Falta-Nainan main road due to laying of primary grid pipeline at Falta Zone-VI under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/003151/2020-2021 | 263/DHSD | 26/11/2020 | 26/12/2020 | CONCORD PROJECTS PRIVATE LIMITED | 4.76 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000359/2023-2024 | 3223/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.31 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-VI of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 1200] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer | ORD/001456/2023-2024 | 2158/AD | 09/08/2023 | 07/11/2023 | MANAS CHATTERJEE | 224.55 | 0 | 0 | 75
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000851/2023-2024 | 789/AD | 03/02/2024 | 03/02/2024 | Resource Division | 14.78 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Construction of 1 no. CWR (200 Cum) at Padmapur Mouza due to improvement of water supply at 5 nos. Mouza i.e. Baidyakhadi, Pakurtala, Padmapur, Abad simulguange and Ahamedpur of Mallickpur G.P. Within Falta Zone-VI Of Falta Block under Diamond Harbour Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001401/2024-2025 | 5525/AD | 28/12/2024 | 23/12/2025 | M/S B.N.ENTERPRISES | 66.07 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Balance works under the Augmentation scheme of Zone-VI at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001406/2024-2025 | 5551/AD | 30/12/2024 | 13/02/2025 | SAFTI PRIVATE LIMITED | 35.97 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Construction of Pump House at CWR (200 Cumec) within Padmapur Mouza of Zone-VI under Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000096/2025-2026 | 2525/AD | 30/05/2025 | 29/06/2025 | K.P. CONSTRUCTION | 5.74 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Supply of 01 No. 450mm sluice valve at the headwork site along with construction of valve chamber and supply & installation of MS ladder inside of OHR at Falta Zone-VI within ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000352/2025-2026 | 251/DHSD | 09/06/2025 | 24/06/2025 | K.P. CONSTRUCTION | 2.06 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF LAYING DISTRIBUTION SYSTEM TO EXTENTED THE BENEFIT OF 100% HOUSEHOLD BY PROVIDING FUNCTIONAL FHTC FOR THE LEFT OUT AREAS IN ZONE- VI AT FALTA BLOCK WITHIN 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR,DISTRICT SOUTH 2 | SM/14902 | Augmentation | Additional balance works under the Augmentation scheme of Zone-VI at Falta block for providing balance pipe laying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000389/2025-2026 | 3374/AD | 16/07/2025 | 30/08/2025 | THE TOWER CONSTRUCTION | 40.87 | 0 | 0 | 0
Total | [13 empty] | 395.11 | 0 | 0