## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ramdebpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 766] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000265/2023-2024 | 3828/AD | 07/11/2023 | 02/09/2024 | CHANDAN ROY | 172.49 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ramdebpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001060/2023-2024 | 3386/AD | 11/10/2023 | 25/11/2023 | DEB ASSOCIATE | 27.5 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Ramdebpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001788/2022-2023 | 3694/AD | 02/08/2022 | 16/09/2022 | INDRANIL DUTTA & ASSOCIATES | 2.63 | 2.63 | 100 | 95
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 653/AD | 17/05/2023 | 17/05/2023 | Resource Division | 4.21 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Material Requisition To Resource Division |  |  | RTOR000462/2023-2024 | 4761/AD | 19/12/2023 | 19/12/2023 | Resource Division | 20.06 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ramdebpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001212/2023-2024 | 3869/AD | 09/11/2023 | 01/11/2025 | SOMNATH ENTERPRISE | 9.47 | 6.61 | 69.77 | 70
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramdebpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001722/2022-2023 | 11748/AD | 21/02/2023 | 07/04/2023 | MODERN CONSTRUCTION (NEW) | 38.59 | 35.01 | 90.73 | 100
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0.16 | 16.65 | 100
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Material Requisition To Resource Division |  |  | RTOR000573/2023-2024 | 74/AD | 03/01/2024 | 03/01/2024 | Resource Division | 0.73 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Material Requisition To Resource Division |  |  | RTOR000958/2023-2024 | 1692/AD | 22/03/2024 | 22/03/2024 | Resource Division | 7.32 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05691/2023-2024 | BP-2023-24-608 | 28/03/2024 | 28/03/2024 | WBSEDCL | 10.32 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Ramdebpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000871/2022-2023 | 364/SMD | 10/02/2023 | 29/09/2025 | KAMAKHYA ENTERPRISE | 18.56 | 0 | 0 | 20
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Ramdebpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002590/2024-2025 | 922/AD | 05/03/2025 | 04/05/2025 | CHANDAN ROY | 60.06 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED WATER SUPPLY SCHEME FOR RAMDEBPUR UNDER ALIPORE DIVISION, PHE DTE, BLOCK-PATHARPRATIMA, DISTRICT-SOUTH 24 PARGANAS | SM/14984 | New | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 & 2 of Ramdevpur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000360/2024-2025 | 2656/SMD | 29/08/2024 | 29/09/2025 | KAMAKHYA ENTERPRISE | 16.86 | 0 | 0 | 100
Total | [13 empty] | 389.75 | 44.41 | 11.39