## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Athara Beki (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001838/2022-2023 | 10937/AD | 06/02/2023 | 23/03/2023 | TECH VISION | 2.82 | 2.82 | 100 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Atharabeki Part-B water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000524/2022-2023 | 393/SMD | 15/02/2023 | 02/04/2026 | CHANDIMATA ELECTRICALS | 21.52 | 0 | 0 | 90
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Laying Distribution System, Providing Functional Household Tap Connection of Ground Water Based Augmentation Piped Water Supply Scheme for Atharabeki (Part - B), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000030/2023-2024 | 169/AD | 19/04/2023 | 18/06/2023 | SAMSUL ENTERPRISE | 120.51 | 81.28 | 67.45 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Atharabeki (Part-B) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000092/2023-2024 | 448/AD | 08/05/2023 | 14/08/2025 | ASHIS ENTERPRISE | 13.07 | 0 | 0 | 65
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Atharabeki (Part-B) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001765/2022-2023 | 12038/AD | 27/02/2023 | 02/01/2025 | BANGA NIRMAN | 7.1 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Atharabenki (Part-B) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001763/2022-2023 | 11945/AD | 24/02/2023 | 30/12/2024 | BANGA NIRMAN | 7.36 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 218/AD | 21/04/2023 | 21/04/2023 | Resource Division | 15.7 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/04679/2023-2024 | BP-2023-24-510 | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.59 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Construction of boundary wall at Pump House No. - 5 at Ground Water Based Augmentation Piped Water Supply Scheme of Atharabeki W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000028/2025-2026 | 2014/AD | 28/04/2025 | 28/05/2025 | HIMALAYAN PROPERTY DEALERS AND PROMOTERS PVT LTD | 14.17 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Supply & fixing main switch & Bus Bar at Pump House-1 & 2 of (Part-B) of Atharabaki water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/14985) | Assistant Engineer | Junior Engineer | ORD/002202/2024-2025 | 288/SMSD | 27/02/2025 | 14/03/2025 | CHANDIMATA ELECTRICALS | 0.59 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House-1 of (Part-B) of Atharabaki water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/14985) | Assistant Engineer | Junior Engineer | ORD/002203/2024-2025 | 286/SMSD | 27/02/2025 | 14/03/2025 | CHANDIMATA ELECTRICALS | 0.92 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House-2 of (Part-B) of Atharabaki water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/14985) | Assistant Engineer | Junior Engineer | ORD/002204/2024-2025 | 287/SMSD | 27/02/2025 | 14/03/2025 | CHANDIMATA ELECTRICALS | 0.92 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF ATHARA BEKI (PART-B) PIPED WATER SUPPLY SCHEME, BLOCK-CANNING-II,DISTRICT-SOUTH 24 PARGANAS | SM/14985 | Augmentation | Quotation for new service( power) connection at Atharabaki Part-B PH-2 Water supply scheme under Canning-II block. Reference ID:-106891613, Application No :-1008312582 |  |  | BILL/03087/2024-2025 | BP-2024-25-624 | 28/03/2025 | 28/03/2025 | WBSEDCL | 4.29 | 0 | 0 | 0
Total | [13 empty] | 2837.06 | 84.1 | 2.96