## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Sagar | S24 Pgns Mechanical | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2, of Ghoramara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I | Junior Engineer | ORD/000352/2022-2023 | 3756/SMD | 29/12/2022 | 29/03/2023 | NITESH MANAGEMENT | 23.19 | 20.65 | 89.02 | 60
2 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households and Construction of Pump House (5.40m. x 3.60m) including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1291] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001745/2022-2023 | 11554/AD | 17/02/2023 | 02/01/2025 | M/S. JHARNA ENTERPRISE | 197.94 | 186.36 | 94.15 | 100
3 | SOUTH 24 PARGANAS | Sagar | S24 Pgns Mechanical | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Supply & delivery of submersible pumping machinery for PH-1 of Ghoramara W/S Scheme under South 24Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000550/2023-2024 | 569/AE-I/SMD. | 11/05/2023 | 26/05/2023 | NITESH MANAGEMENT | 0.65 | 0.65 | 100 | 100
4 | SOUTH 24 PARGANAS | Sagar | S24 Pgns Mechanical | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Supply & installation of automatic chlorinator for PH-2 of Ghoramara W/S Scheme under South 24Pgs Mechanical Division, PHE Dte. | Assistant Engineer -I | Junior Engineer | ORD/000551/2023-2024 | 568/AE-I/SMD. | 11/05/2023 | 26/05/2023 | NITESH MANAGEMENT | 1 | 1 | 100 | 100
5 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Supplying, fitting, fixing and delivery of different dia. specials for Ghoramara W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001000/2023-2024 | 507/KSD | 03/10/2023 | 10/10/2023 | M/S. JHARNA ENTERPRISE | 3.87 | 2.5 | 64.61 | 100
6 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site of Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001531/2022-2023 | 11021/AD | 08/02/2023 | 25/03/2023 | HARIDAS DUTTA | 47.07 | 42.95 | 91.24 | 92
7 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Continuation work order for Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households and Construction of Pump House (5.40m. x 3.60m) including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1291] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001174/2023-2024 | 1037/AD | 13/06/2023 | 28/07/2023 | M/S. JHARNA ENTERPRISE | 39.71 | 39.56 | 99.62 | 100
8 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Making and fixing of permanent display board at headwork site of Shibpur Zone - I & II, Ghoramara PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002175/2023-2024 | 954/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.61 | 0.2 | 33.33 | 100
9 | SOUTH 24 PARGANAS | Sagar | S24 Pgns Mechanical | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Supply & delivery of pumping accessories at PH-2 of Ghoramara W/S Scheme under JJM under South 24-Pgs Mechanical Division, PHE Dte. [Block- Sagar] | Assistant Engineer -I | Junior Engineer | ORD/002033/2023-2024 | 680-AE-I-SMD | 21/06/2023 | 06/07/2023 | NITESH MANAGEMENT | 0.23 | 0.23 | 96.94 | 98
10 | SOUTH 24 PARGANAS | Sagar | S24 Pgns Mechanical | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Supply & installation of LED board at PH-1&2 of Ghoramara W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.[Block-Sagar] |  |  | ORD/001788/2023-2024 | 1030/AE-I/SMD | 20/09/2023 | 05/10/2023 | GHOSH ENTERPRISE | 0.82 | 0.82 | 100 | 100
11 | SOUTH 24 PARGANAS | Sagar | S24 Pgns Mechanical | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Supply & delivery of pumping accessories at PH-1 of Ghoramara W/S Scheme under JJM under South 24-pgs Mechanical Division, PHE Dte. [Block-Sagar] | Assistant Engineer -I | Junior Engineer | ORD/002034/2023-2024 | 681-AE-I-SMD | 21/06/2023 | 06/07/2023 | NITESH MANAGEMENT | 0.23 | 0.23 | 96.94 | 98
12 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Construction of Household Tap Platform etc. at different household for Ghoramara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14988) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000143/2024-2025 | 2481/AD | 14/06/2024 | 02/04/2025 | M/S. JHARNA ENTERPRISE | 71.83 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ghoramara W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002180/2023-2024 | 816/AD | 05/02/2024 | 02/02/2025 | TAPAS KUMAR PRADHAN | 11.71 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ghoramara W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002428/2023-2024 | 1458/AD | 11/03/2024 | 31/12/2024 | ADRIJA ENTERPRISE | 31.62 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Material Requisition To Resource Division |  |  | RTOR000527/2023-2024 | 12/AD | 02/01/2024 | 02/01/2024 | Resource Division | 7.67 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Material Requisition To Resource Division |  |  | RTOR000973/2023-2024 | 1766/AD | 27/03/2024 | 27/03/2024 | Resource Division | 30.41 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Sagar | Alipore Division | GHORAMARA PIPED WATER SUPPLY SCHEME IN SAGAR BLOCK IN SOUTH 24 PARGANAS, WEST BENGAL UNDER ALIPORE DIVISION, PHE DTE. | SM/14988 | New | Providing support services for data mapping of available data within command area for preparation of GMIS at Dhaspara (Zone-I and II) (SM/15221), Ghoramara (SM/14988) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000020/2025-2026 | 2006/AD | 28/04/2025 | 28/05/2025 | ROY CHOWDHURY ASSOCIATES | 7.24 | 0 | 0 | 100
Total | [13 empty] | 475.78 | 295.14 | 62.03