## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Dharmatala (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001840/2022-2023 | 10939/AD | 06/02/2023 | 23/03/2023 | TECH VISION | 4.2 | 4.2 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001348/2022-2023 | 10215/AD | 19/01/2023 | 20/03/2023 | B.K. ENTERPRISE. | 59.91 | 53.85 | 89.89 | 90
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 271/AD | 24/04/2023 | 24/04/2023 | Resource Division | 16.49 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01727/2023-2024 | BP-2023-24-193 | 09/08/2023 | 09/08/2023 | WBSEDCL | 22.37 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Supply delivery of standby submersible pump motor at Aug of Dharmatala( Part-B) PH-2 water supply scheme Under SMD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000330/2024-2025 | 1033/SMSD | 15/07/2024 | 30/07/2024 | ARUSHI CONSTRUCTION | 0.58 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001582/2022-2023 | 10781/AD | 03/02/2023 | 20/03/2023 | MAA SOLAR ENTERPRISE | 7.02 | 6.55 | 93.25 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001583/2022-2023 | 10782/AD | 03/02/2023 | 20/03/2023 | MAA SOLAR ENTERPRISE | 7.02 | 6.86 | 97.63 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001822/2022-2023 | 12337/AD | 06/03/2023 | 20/04/2023 | M/S ARIYAN ENTERPRISE | 7.35 | 7.27 | 98.94 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1,2 & 3 for Augmentation of Dharmatala ( Part-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000033/2023-2024 | 983/SMD | 05/04/2023 | 04/07/2023 | M/S.UTTAM KUMAR CHATTERJEE | 29.05 | 28.1 | 96.74 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Construction of Boundary Wall and Renovation of Pump House No. 4 at Dharmatala W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001406/2023-2024 | 1145/CSD | 01/11/2023 | 01/12/2023 | GOUTAM HALDAR (I) | 3.8 | 3.8 | 99.93 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Dharmatala PH-2 under Canning-I Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002256/2023-2024 | 1626/SMSD | 29/12/2023 | 13/01/2024 | M/S.UTTAM KUMAR CHATTERJEE | 0.88 | 0.88 | 100 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Dharmatala PH-3 under Canning-I Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002257/2023-2024 | 1625/SMSD | 29/12/2023 | 13/01/2024 | M/S.UTTAM KUMAR CHATTERJEE | 0.88 | 0.88 | 100 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for Dharmatala (Part-B), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1544] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000028/2023-2024 | 156/AD | 18/04/2023 | 01/08/2025 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 244.1 | 0 | 0 | 20
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Dharmatala (Part-B) W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000095/2023-2024 | 451/AD | 08/05/2023 | 23/05/2023 | GOUTAM HALDAR (I) | 12.74 | 6.95 | 54.57 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 03/11/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 0 | 30
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF DHARMATALA (PART-B) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15043 | Augmentation | Laying of pipeline within some uncovered habitation for Functional Household Tap Connection at Augmentation of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000218/2023-2024 | 1023/AD | 13/06/2023 | 04/03/2025 | GOUTAM HALDAR (I) | 12.65 | 0 | 0 | 100
Total | [13 empty] | 3053.54 | 119.34 | 3.91