## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households in Garan Bose Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division |  | ORD/001301/2020-2021 | 2275/AD | 12/10/2020 | 12/10/2021 | M/S. BLUE BELL ENTERPRISE | 136.08 | 16.52 | 12.14 | 63
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001712/2022-2023 | 11676/AD | 20/02/2023 | 06/04/2023 | BABAMONI CONSTRUCTION | 7.1 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | inking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Goran Bose W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001670/2022-2023 | 11481/AD | 15/02/2023 | 21/03/2025 | RAHAMAN ENTERPRISE | 39.19 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Goranbose water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 953/SMD | 04/04/2023 | 03/07/2023 | KARUNAMOY ENGINEERING | 26.02 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002043/2022-2023 | 13043/AD | 24/03/2023 | 08/05/2023 | SUNNY CONSTRUCTION | 42.98 | 16.41 | 38.17 | 40
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (620 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Goranbose Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002003/2022-2023 | 12817/AD | 16/03/2023 | 30/04/2023 | MS SINHA ROY & CO | 49.13 | 17.09 | 34.78 | 40
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 246/AD | 24/04/2023 | 24/04/2023 | Resource Division | 81.96 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Goranbose W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15044) | Assistant Engineer | Junior Engineer | ORD/001172/2024-2025 | 122/SMSD | 22/01/2025 | 06/02/2025 | KARUNAMOY ENGINEERING | 0.96 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-1 of Goranbose W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15044) | Assistant Engineer | Junior Engineer | ORD/001171/2024-2025 | 121/SMSD | 22/01/2025 | 06/02/2025 | KARUNAMOY ENGINEERING | 0.96 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1 & 2 of Goranbose W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti)(SM/15044) | Assistant Engineer | Junior Engineer | ORD/001170/2024-2025 | 120/SMSD | 22/01/2025 | 06/02/2025 | KARUNAMOY ENGINEERING | 0.58 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Surging of 01 no. Big dia Tubewell of Goranbose (TW-1) W/S Scheme, Block - Basanti of Canning Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000060/2025-2026 | 539/CSD | 29/04/2025 | 29/05/2025 | S.K.GOLUI | 2.29 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Surging of 01 no. Big dia Tubewell of Goranbose (TW-2) W/S Scheme, Block - Basanti of Canning Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000061/2025-2026 | 540/CSD | 29/04/2025 | 29/05/2025 | S.K.GOLUI | 2.29 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF GORANBOSE PWSS FOR PROVIDING FHTC BLOCK-BASANTI | SM/15044 | Augmentation | Charges for service connection at pump house no-4 of Goranbose water supply scheme (Basanti Block) |  |  | BILL/02532/2024-2025 | BP-2024-25-558 | 28/01/2025 | 28/01/2025 | WBSEDCL | 13.81 | 0 | 0 | 0
Total | [13 empty] | 403.36 | 50.02 | 12.4