## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 121/AD | 13/04/2023 | 13/04/2023 | Resource Division | 0.34 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 220/AD | 21/04/2023 | 21/04/2023 | Resource Division | 61.12 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 853/AD | 27/05/2023 | 27/05/2023 | Resource Division | 1.72 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Narayanpur W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001682/2022-2023 | 11489/AD | 15/02/2023 | 01/04/2023 | R CONSTRUCTION | 7.11 | 0 | 0 | 98
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Narayanpur W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001663/2022-2023 | 11475/AD | 15/02/2023 | 17/03/2023 | SARFARAZ CONSTRUCTION | 19.59 | 18.77 | 95.82 | 90
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H.1 for Augmentation of Narayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000288/2023-2024 | 1148/SMD | 24/04/2023 | 05/08/2025 | NITESH MANAGEMENT | 11.16 | 5.87 | 52.59 | 95
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Inter connection and rising main with supply of specials at PH-IV of Narayanpur W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000734/2023-2024 | 2895/AD | 19/09/2023 | 03/11/2023 | DIPTI ENTERPRISE | 70.53 | 0 | 0 | 60
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Pump House- 1 of Aug of Narayanpur water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15045) | Assistant Engineer | Junior Engineer | ORD/001771/2024-2025 | 71/SMSD | 17/01/2025 | 01/02/2025 | NITESH MANAGEMENT | 0.92 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Construction of boundary wall and Land development for Tube Well No. 4 Site at Narayanpur W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000311/2025-2026 | 2964/AD | 25/06/2025 | 25/07/2025 | CHATTERJEE CONSTRUCTION | 19.11 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Supply & fixing main switch & Bus Bar at Pump House- 1 of Aug of Narayanpur water supply sche under SMD,PHE Dte. (Block-Canning-II) (SM/15045) | Assistant Engineer | Junior Engineer | ORD/001770/2024-2025 | 70/SMSD | 17/01/2025 | 01/02/2025 | NITESH MANAGEMENT | 0.29 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF NARAYANPUR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15045 | Augmentation | Relaying of pipeline, damaged due to construction of culvert by PWD of Narayanpur W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002552/2024-2025 | 1415/CSD | 10/12/2024 | 04/01/2025 | SUJOY SADHUKHAN | 0.49 | 0 | 0 | 98
Total | [13 empty] | 192.37 | 24.64 | 12.81