## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | SM/15050 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation at Ramchandrapur W/S Scheme, Block - Kakdwip for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000164/2023-2024 | 608/AD | 15/05/2023 | 14/06/2023 | KALACHAND DAS | 19.29 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | SM/15050 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Ramchandrapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000050/2023-2024 | 1046/SMD | 17/04/2023 | 16/07/2023 | PURUSHOTTAM ENTERPRISE | 8.91 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | SM/15050 | New | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 663/AD | 17/05/2023 | 17/05/2023 | Resource Division | 1.21 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | SM/15050 | New | Material Requisition To Resource Division |  |  | RTOR000458/2023-2024 | 4721/AD | 18/12/2023 | 18/12/2023 | Resource Division | 1.42 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | SM/15050 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ramchandrapur W/S Scheme, Block - Kakdwip for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15050) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000645/2024-2025 | 4141/AD | 05/10/2024 | 30/01/2025 | S. CHAKRABORTY AND CO. | 20.41 | 4.91 | 24.07 | 100
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | SM/15050 | New | Material Requisition To Resource Division |  |  | RTOR000817/2023-2024 | 662/AD | 30/01/2024 | 30/01/2024 | Resource Division | 1.24 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | SM/15050 | New | Laying distribution system, construction of 01 no. pump house size 5.40mtr. x 3.60 mtr., Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution and FHTC for 1 year after completion of FHTC works for Ramchandrapur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001426/2023-2024 | 4605/AD | 14/12/2023 | 25/06/2026 | R.S.CONSTRUCTION CO. | 60.7 | 0 | 0 | 50
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR RAMCHANDRAPUR, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS. | SM/15050 | New | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0 | 0 | 100
Total | [13 empty] | 114.13 | 4.91 | 4.31