## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-V) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001916/2022-2023 | 10942/AD | 06/02/2023 | 23/03/2023 | INDRANIL DUTTA & ASSOCIATES | 7.26 | 0 | 0 | 99
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 1050/AD | 15/06/2023 | 15/06/2023 | Resource Division | 13.83 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 231/AD | 24/04/2023 | 24/04/2023 | Resource Division | 24.45 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-V) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001726/2022-2023 | 11763/AD | 21/02/2023 | 12/05/2023 | B.K. ENTERPRISE. | 60 | 0 | 0 | 97
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002047/2022-2023 | 13047/AD | 24/03/2023 | 08/05/2023 | JAGANNATH CONSTRUCTION | 7.11 | 0 | 0 | 98
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002048/2022-2023 | 13048/AD | 24/03/2023 | 08/05/2023 | SABITA INFRASTRUCTURE | 7.11 | 0 | 0 | 98
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Charges for service connection at Pump house no-1 of Basant (Zone-V) |  |  | BILL/00446/2024-2025 | BP-2024-25-114 | 14/06/2024 | 14/06/2024 | WBSEDCL | 5.46 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Charges for new service connection at pump house no-2 of Basanti (Zone-V) water supply scheme. |  |  | BILL/01806/2024-2025 | BP-2024-25-443 | 07/10/2024 | 07/10/2024 | WBSEDCL | 13.64 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Charges for New service connection at Pump house no-3 of Basanti (Zone-V) water supply scheme. |  |  | BILL/01153/2024-2025 | BP-2024-25-234 | 08/08/2024 | 08/08/2024 | WBSEDCL | 8.89 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD |  |  | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001703/2022-2023 | 11667/AD | 20/02/2023 | 06/04/2023 | SARKAR CONSTRUCTION | 7.36 | 0 | 0 | 99
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 05/01/2026 | M/S PATH MAKERS | 2061.38 | 0 | 0 | 78
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2 & 3 for Augmentation of Basanti (Zone-5) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000020/2023-2024 | 955/SMD | 04/04/2023 | 01/06/2025 | A.S.ENTERPRISE | 29.02 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-V) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000093/2023-2024 | 449/AD | 03/05/2023 | 16/12/2024 | HI TECH ENTERPRISE | 9.12 | 0 | 0 | 90
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Supply & delivery of Actuator Valve at Pump House no-3 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer | Junior Engineer | ORD/001202/2024-2025 | 1654/SMSD | 13/12/2024 | 16/02/2025 | A.S.ENTERPRISE | 0.99 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-1 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer | Junior Engineer | ORD/001209/2024-2025 | 1650/SMSD | 13/12/2024 | 28/12/2024 | A.S.ENTERPRISE | 0.59 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Improvement of outdoor Illumination arrangement with allied works at Pump House no-2 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer | Junior Engineer | ORD/001208/2024-2025 | 112/SMSD | 22/01/2025 | 06/02/2025 | A.S.ENTERPRISE | 0.85 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-2 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer | Junior Engineer | ORD/001210/2024-2025 | 110/SMSD | 22/01/2025 | 06/02/2025 | A.S.ENTERPRISE | 0.59 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Supply & delivery of column pipe ,Sluice Valve,Non return at Pump House no-3 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer | Junior Engineer | ORD/001212/2024-2025 | 111/SMSD | 22/01/2025 | 06/02/2025 | A.S.ENTERPRISE | 0.59 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Supply & Fixing main switch & Bus bar at Pump House no-1,2 & 3 of Basanti Aug (Zone-5) W/S Scheme under SMD, P.H.E. Dte.(Block-Basanti) | Assistant Engineer | Junior Engineer | ORD/001213/2024-2025 | 1649/SMSD | 13/12/2024 | 16/02/2025 | A.S.ENTERPRISE | 0.87 | 0 | 0 | 100
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Supply & delivery of Actuator Valve at Pump House no-1 of Basanti (Zone-V) W/S scheme under SMD, P.H.E. Dte.(Block-Basanti) (SM/15052) | Assistant Engineer | Junior Engineer | ORD/001204/2024-2025 | 1652/SMSD | 13/12/2024 | 28/12/2024 | A.S.ENTERPRISE | 0.99 | 0 | 0 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION & RETROFITTING OF BASANTI (ZONE-V) PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/15052 | Augmentation | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 11/02/2025 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 0 | 99
Total | [13 empty] | 2789.56 | 0 | 0